## Introduction
JCC PHOENIX SAP HANA CLOUD |  | System Implementation
Introduction
PURPOSE |  | The purpose of this document is to identify and document the project requirements to include Business, Functional and Non-Functional requirement, for the Phoenix project.
Version | 1 | SP version 1
TOC
Req Type | Worksheet Name | Worksheet Description | Vendor Response Code & Comment column Entries Required
Migration | Prepare | Preparation Phase | Yes
Migration | Explore | Explore Phase | Yes
Migration | Realize | Project Realization | Yes
Migration | Final Preparation | Final Preparation | Yes
Migration | Go-Live | Go-Live | Yes
n/a
n/a
Vendor Response Codes
Response Code | Response | Response Code Definition | Vendor Response Comment
Y | Yes | The requirement will be fully met -or Designated responsibility is fully accepted | {optional}
N | No | The requirement will NOT be fully met -or Designated responsibility cannot be fully accepted | {encouraged}
P | Partial | Requirement or Responsibility can only be partially met. The respondent must provide a detailed explanation. | {detailed explanation required}
Priority |  | Every requirement designated with an RQM-ID in the RTM has been given a “Priority” rating from 1 to 4, indicating the JCC desirability. A priority 1 indicates a Mandatory requirement while a 4 is the lowest rating.
Priority Rating | Priority Type | Definition
1 | Mandatory | Mandatory Requirement / Respondent may be disqualified for not meeting requirement
2 | Highly Desirable | High Priority Requirement. Very important but not a disqualifiable Requirement.
3 | Preferred | Preferred Priority Requirement
4 | Minor | Minor Priority Requirement / Nice to Have
Categories | Description
A | Business Health, Company Profile and Experience
B | Migration Support, Vendor Lock-In & Exit Planning
C | Reliability, Disaster Recovery & Performance
D | Contracts, Commercials (Service Bundles) & SLAs (SLOs and Remedies)
E | Service Dependencies and Partnerships
F | Data Governance and Security
G | Technologies & Service Roadmap
H | Business Functional Requirements
I | Certifications & Standards
Sub Categories | Description
1.7.0 | Business Functional Requirements | 1.7.0 Business Functional Requirements
1.7.4 | Move-Stay | 1.7.4 Move-Stay
1.7.5 | New Licenses | 1.7.5 New Licenses
1.7.6 | License Transfer Policies | 1.7.6 License Transfer Policies
1.7.7 | 3rd-party tools | 1.7.7 3rd-party tools
1.7.8 | Sizing (Current, Future) | 1.7.8 Sizing (Current, Future)
1.7.9 | Hosting (Type, Location, Continuity, Latency) | 1.7.9 Hosting (Type, Location, Continuity, Latency)
1.7.10 | SLO / SLR / SLA Requirements | 1.7.10 SLO / SLR / SLA Requirements
1.7.10.1 | Refresh of Environments | 1.7.10.1 Refresh of Environments
1.7.10.2 | Security Administration | 1.7.10.2 Security Administration
1.7.10.3 | Change Requests | 1.7.10.3 Change Requests
1.7.10.4 | Incident Resolution | 1.7.10.4 Incident Resolution
1.7.10.5 | Root Cause Analysis | 1.7.10.5 Root Cause Analysis
1.7.10.6 | Provisioning | 1.7.10.6 Provisioning
1.7.10.7 | Backup and Retention | 1.7.10.7 Backup and Retention
1.7.10.8 | Disaster Recovery | 1.7.10.8 Disaster Recovery
1.7.10.9 | Business Continuity | 1.7.10.9 Business Continuity
1.7.10.10 | Availability | 1.7.10.10 Availability
1.7.10.11 | Deployment Speed | 1.7.10.11 Deployment Speed
1.7.10.12 | Performance | 1.7.10.12 Performance
1.7.10.13 | Help Desk | 1.7.10.13 Help Desk
1.7.10.14 | Account Administration | 1.7.10.14 Account Administration
1.7.10.15 | SAP Administration | 1.7.10.15 SAP Administration
1.7.13 | Supplier Experience and Capabilities | 1.7.13 Supplier Experience and Capabilities
1.7.15 | Technical and Functional Requirements | 1.7.15 Technical and Functional Requirements
1.7.15.2 | Gartner Cloud Infrastructure Requirements (Prototypes) | 1.7.15.2 Gartner Cloud Infrastructure Requirements (Prototypes)
1.7.15.2.1 | Baseline | 1.7.15.2.1 Baseline
1.7.15.2.2 | Compute | 1.7.15.2.2 Compute
1.7.15.2.3 | Storage | 1.7.15.2.3 Storage
1.7.15.2.4 | Network | 1.7.15.2.4 Network
1.7.15.2.6 | Security | 1.7.15.2.6 Security
1.7.15.2.6.1 | Applicable Industry, Standard-Body Standards | 1.7.15.2.6.1 Applicable Industry, Standard-Body Standards
1.7.15.2.6.2 | Authentication | 1.7.15.2.6.2 Authentication
1.7.15.2.6.3 | Encryption | 1.7.15.2.6.3 Encryption
1.7.15.2.6.4 | Access | 1.7.15.2.6.4 Access
1.7.15.2.6.5 | Remote Access | 1.7.15.2.6.5 Remote Access
1.7.15.2.6.6 | Mitigation | 1.7.15.2.6.6 Mitigation
1.7.15.2.7 | Software Infrastructure Services | 1.7.15.2.7 Software Infrastructure Services
1.7.15.2.8 | Operations Management | 1.7.15.2.8 Operations Management
1.7.15.2.9 | Vendor Management and Support | 1.7.15.2.9 Vendor Management and Support
1.7.15.2.10 | Compliance and Documentation | 1.7.15.2.10 Compliance and Documentation
1.7.15.2.11 | Service Offerings | 1.7.15.2.11 Service Offerings
1.7.15.2.12 | Support and Service Levels | 1.7.15.2.12 Support and Service Levels
1.7.15.2.13 | Management and DevOps | 1.7.15.2.13 Management and DevOps
1.7.15.2.14 | Price and Billing | 1.7.15.2.14 Price and Billing
1.7.15.3 | Storage | 1.7.15.3 Storage
1.7.15.4 | Virtual Machine | 1.7.15.4 Virtual Machine
1.7.15.5 | Virtual Network | 1.7.15.5 Virtual Network
1.7.15.6 | Platform as a Service | 1.7.15.6 Platform as a Service
1.7.15.7 | Security | 1.7.15.7 Security
1.7.15.8 | Data Management | 1.7.15.8 Data Management
1.7.15.9 | Monitoring and Updating Service Status | 1.7.15.9 Monitoring and Updating Service Status
1.7.15.10 | Additional Backup Services | 1.7.15.10 Additional Backup Services
1.7.15.11 | Disaster Recovery and Business Continuity | 1.7.15.11 Disaster Recovery and Business Continuity
1.7.15.12 | Additional Disaster Recovery Services | 1.7.15.12 Additional Disaster Recovery Services
1.7.15.13 | Managed Solution | 1.7.15.13 Managed Solution
1.7.15.14 | Other Services | 1.7.15.14 Other Services
1.7.15.15 | Transition and Implementation | 1.7.15.15 Transition and Implementation
1.7.15.16 | Migration Services | 1.7.15.16 Migration Services
1.7.15.17 | Database Management | 1.7.15.17 Database Management
1.7.15.18 | Optional Collaborative Initiatives | 1.7.15.18 Optional Collaborative Initiatives
1.7.15.19 | Technology Refresh | 1.7.15.19 Technology Refresh
1.7.15.20 | Invoicing (T's &C's) | 1.7.15.20 Invoicing (T's &C's)
1.7.15.21 | Payment Terms (T's &C's) | 1.7.15.21 Payment Terms (T's &C's)
1.7.15.22 | Agreement Administration and Support to Client | 1.7.15.22 Agreement Administration and Support to Client
1.7.15.23 | Customer Support | 1.7.15.23 Customer Support
1.7.15.24 | Reporting to Clients | 1.7.15.24 Reporting to Clients
1.7.15.25 | Agreement Management Support to JCC | 1.7.15.25 Agreement Management Support to JCC
1.7.15.26 | Account Management Support | 1.7.15.26 Account Management Support
1.7.15.27 | Performance Management | 1.7.15.27 Performance Management
1.7.15.28 | Reporting to JCC | 1.7.15.28 Reporting to JCC
1.7.15.29 | Unilateral Amendments to Service Features | 1.7.15.29 Unilateral Amendments to Service Features
1.7.15.30 | Termination | 1.7.15.30 Termination
1.7.15.31 | Licenses, Right to Use and Approvals | 1.7.15.31 Licenses, Right to Use and Approvals
1.7.15.32 | Accessibility for Americans with Disabilities Act | 1.7.15.32 Accessibility for Americans with Disabilities Act
1.7.15.33 | Pricing Methodology | 1.7.15.33 Pricing Methodology
1.7.15.34 | Optional List Price Refresh | 1.7.15.34 Optional List Price Refresh
1.7.15.35 | Optional Pricing Refresh | 1.7.15.35 Optional Pricing Refresh
1.7.15.36 | Quick Quote Process | 1.7.15.36 Quick Quote Process
1.7.15.37 | Network | 1.7.15.37 Network
1.7.15.38 | Monitoring | 1.7.15.38 Monitoring
1.7.15.39 | Analytics | 1.7.15.39 Analytics
1.7.15.40 | Business Process Review and Improvement | 1.7.15.40 Business Process Review and Improvement
1.7.15.41 | Transformation, Conversion, Fit-to-Standard | 1.7.15.41 Transformation, Conversion, Fit-to-Standard
1.7.15.42 | Integration and Interfaces | 1.7.15.42 Integration and Interfaces
1.7.15.43 | Report Modifications | 1.7.15.43 Report Modifications
1.7.15.44 | Code Analysis | 1.7.15.44 Code Analysis
1.7.15.45 | Governance | 1.7.15.45 Governance
1.7.15.46 | Migration Data Validation | 1.7.15.46 Migration Data Validation
1.7.15.47 | Greenfield, Brownfield, Lift and Shift Cost Analysis | 1.7.15.47 Greenfield, Brownfield, Lift and Shift Cost Analysis
1.7.15.48 | Analyze and Document Existing Cost Variables | 1.7.15.48 Analyze and Document Existing Cost Variables
1.7.15.49 | Pricing Plans (M&O) OPEX) | 1.7.15.49 Pricing Plans (M&O) OPEX)
1.7.15.49.1 | Pay Per Use | 1.7.15.49.1 Pay Per Use
1.7.15.49.2 | On-Demand | 1.7.15.49.2 On-Demand
1.7.15.49.3 | Dedicated Instance | 1.7.15.49.3 Dedicated Instance
1.7.15.49.4 | Spot Instance | 1.7.15.49.4 Spot Instance
1.7.15.49.5 | Reservation | 1.7.15.49.5 Reservation
1.7.15.49.6 | Handling unused capacity | 1.7.15.49.6 Handling unused capacity
1.7.15.50 | Migration Sequencing and Dependencies | 1.7.15.50 Migration Sequencing and Dependencies
1.7.15.51 | Mock Migrations | 1.7.15.51 Mock Migrations
1.7.15.52 | Staffing - Migration | 1.7.15.52 Staffing - Migration
1.7.15.53 | Staff Training - Migration | 1.7.15.53 Staff Training - Migration
1.7.15.54 | Staffing - Steady State | 1.7.15.54 Staffing - Steady State
1.7.15.55 | Staff Training - Steady State | 1.7.15.55 Staff Training - Steady State
1.7.16 | Remediation, Testing | 1.7.16 Remediation, Testing
Responsible
Supports
Informed
*INSTRUCTION NOTES:
1. Each worksheet in this workbook requires the Response Vendor to select a “Vendor Response Code” and provide “Vendor Response Comments” for the RFP
(Please see both Vendor Response Codes tables for definition in the Introduction worksheet).
2. Please provide detailed explanation in the “Vendor Response Comment” column if the response code selected is other than “Y”.
3. Submissions of the *.xlsx file format is requested. The *.xlsx can be printed/exported as a *.pdf file to include as part of your submission.
Thank You,
Judicial Council, Branch Accounting and Procurement Office

## 2.9.1 Prepare
RQM-ID | Category Code | Category of Requirements | Requirement Description | Priority # | Priority | SubType Category | Req Type Classification | Vendor | JCC | SoH | S/4 | Vendor Response Code | Vendor Response Category | Vendor Response Comments | PC
2.9.1.1 | E | Service Dependencies and Partnerships | Include advisory services of the software vendor SAP, such as support of the HANA Ambassador program, or placement of SAP consulting resource(s) in key project team positions, (for scenario 2, SAP S/4HANA system migration). | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.2 | B | Migration Support, Vendor Lock-In & Exit Planning | At all times comply with California SB1386 (Data Security Breach Reporting). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.3 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Project Manager (PM) to represent the Bidder in the management of the project, interfacing with the JCC PM in any decisions relating to the project. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.4 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Project Manager to represent the JCC business units in this project, interfacing with the Bidder’s PM, and representing the JCC in any decisions relating to the project. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.5 | B | Migration Support, Vendor Lock-In & Exit Planning | Assume and lead all day-to-day management of all Vendor personnel, including subcontractor personnel, and associated deliverables related to the required services. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.6 | B | Migration Support, Vendor Lock-In & Exit Planning | Obtain oversight and approval through coordination with the program management office and executive management. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.7 | B | Migration Support, Vendor Lock-In & Exit Planning | Interface with and support requests from the Project Manager as requested by the JCC. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.8 | B | Migration Support, Vendor Lock-In & Exit Planning | Follow SAP’s Activate project ALM management methodology. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.9 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a robust project management methodology and toolkit founded on industry best practices. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.10 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct project management activities throughout the lifecycle and execute the associated plans. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.11 | B | Migration Support, Vendor Lock-In & Exit Planning | Establish a formal requirements management process that shall include: -Assumption Definition, Tracking, and Traceability -Business and Technical Requirement Definition, Tracking, Traceability, and Verification -Operational Change Process -Phase and Product Entry and Exit (Acceptance) Criteria Definition, Tracking and Signoff | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.12 | B | Migration Support, Vendor Lock-In & Exit Planning | Establish a Key-Decisions Roadmap of critical decisions that will be required of key stakeholders over the course of the Project. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.13 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Project Charter that outlines the scope, timeline, objectives, organization structure, project approach, high-level deliverables, resources, and governance structure. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.14 | B | Migration Support, Vendor Lock-In & Exit Planning | Align Stakeholders with the Governance structure developed for the Project and Key Decision Makers. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.15 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Project Operational Change Plan that defines roles, responsibilities for establishing procedures and managing Operational Change requests. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.16 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide, update, and maintain throughout the lifecycle of the project a Project Schedule which is consistent with SAP’s Activate ALM and includes, but is not limited to the following components: -Tasks -Activities -Milestones -Resources -Dependencies -Task and activity durations -Critical path identification -Templates | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.17 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide, update, and maintain a formal, comprehensive Project Management Plan (PMP) for migration and onboarding activities that includes (but is not limited to) the following key components: -Bidder and subcontractor management -Budget management, expenditure control, and Earned Value as mutually agreed upon by the JCC and Bidder -Critical path identification, and dependencies -Current project schedule -Deliverable/product review and approval and other acceptance criteria -Issue tracking, escalation, and resolution -Operational change request approval and tracking -Project initiation activities -Project success evaluation criteria and project close-out activities -RACI (Responsible, Accountable, Consulted, Informed) of all JCC, Vendor and 3PP Roles and Responsibilities -Relationships to other IT or business efforts -Schedule/milestone tracking and resource allocation -Status and other reporting activities | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.9.1.18 | B | Migration Support, Vendor Lock-In & Exit Planning | Identify contacts within the Cloud Provider organization for architecture and design of the solution. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.19 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Risk Management Plan that shall be used, quantify the potential impact of each identified risk, present mitigation plans for each identified risk, and enact appropriate risk responses. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.9.1.20 | B | Migration Support, Vendor Lock-In & Exit Planning | Implement risk mitigation measures and contingency plans as high-priority risks are identified and monitored. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.21 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide an Issue Management and Resolution Strategy and process including identification, tracking, and resolution of issues. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.22 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide formal Training and Knowledge Transfer Strategy and Plans to document training requirements and the approach the JCC support organization will use for updating training requirements, development of training curricula, and deploying training for the JCC’s support staff as required. Include specific knowledge transfer milestones with clear deliverables for each set of activities that will be owned by the JCC. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.9.1.23 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Master Test Strategy that describes the approach that will be taken to fully test all components of the system including test control and approval processes, test participants, how testing will interface with the configuration management process, and test documentation expectations for the following test types: unit, functional, volume, end-to-end, document conversion/migration validation, security, integration, response time & capacity, regression, and user acceptance. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.9.1.24 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide formal Communication Strategy and Plans that shall be used to communicate with all project stakeholders throughout the life of the project including, at a minimum, the following activities: -Communication with internal and external stakeholders -Formal kickoffs of phases -Communication of milestones -Status reports | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.25 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Quality Management Plan that designates a Quality Management Planning Team (made up of Bidder and JCC staff) and a liaison to work with JCC staff to resolve any emerging problems or areas of concern and to ensure standards are being met. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.26 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a description of how Operational Changes resulting from problem-solving or process improvement will be documented and approved. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.27 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Project Status Reports and conduct regularly scheduled status meetings reviewing project progress, planned activities, major milestones, and project deliverables, all critical path dependencies and bottlenecks, staffing resources, risk management, issues/issue resolution, and next steps. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.28 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide weekly status reviews, issues logs, and progress reports at the sub-team level (e.g. Phoenix functional teams, technical team, deployment team). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.29 | B | Migration Support, Vendor Lock-In & Exit Planning | Use the JCC’s repository to store, organize, track, control and disseminate all information and items produced by and delivered to the project. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.30 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a toolset to support project activities such as issues management, requirements management, and change management, etc., accessible by all internal and external project team members. The data will be provided to the JCC upon completion of the project. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.31 | B | Migration Support, Vendor Lock-In & Exit Planning | Ensure alignment of the system with JCC’s technical architecture, security guidelines and IT policies and procedures Judicial Branch Information Systems Controls Framework (Exhibit 13). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.32 | B | Migration Support, Vendor Lock-In & Exit Planning | Communicate project scope change process and procedures to JCC stakeholders. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.33 | B | Migration Support, Vendor Lock-In & Exit Planning | Prepare and track JCC change requests and document impact analysis associated with proposed changes. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.34 | B | Migration Support, Vendor Lock-In & Exit Planning | Approve and prioritize changes. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.35 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide all training necessary to ensure that Bidder project team members are appropriately skilled and knowledgeable on all industry-standard and related best practice components utilized in establishing the Phoenix test environments and the supporting platform. This also includes best practices on business processes and the configuration of Phoenix to meet JCC business requirements. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.9.1.36 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide and document a Business Process and Organizational Change Management Strategy. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.37 | B | Migration Support, Vendor Lock-In & Exit Planning | Lead business process and organizational change management activities. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.38 | B | Migration Support, Vendor Lock-In & Exit Planning | Document deliverable details, formats, and acceptance criteria. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.9.1.39 | B | Migration Support, Vendor Lock-In & Exit Planning | Approve all Templates, Formats and Materials to be submitted to support Deliverables Acceptance. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>

## 2.10.1 Explore
RQM-ID | Category Code | Category of Requirements | Requirement Description | Priority # | Priority | SubType Category | Req Type Classification | Vendor | JCC | SoH | S/4 | Vendor Response Code | Vendor Response Category | Vendor Response Comments | SL
2.10.1.1 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Business Solution that shall define the overall design for the implementation of the Project, including at a minimum: -Business and architectural end-state design for the Phoenix system -Reporting strategy -Onboarding and Migration activities -Migration approach -Optimized TCO emphasizing reduction in interim on-premise and cloud hosting costs | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.2 | B | Migration Support, Vendor Lock-In & Exit Planning | Engage Cloud Services Provider for Architectural and Design assistance: -Target Cloud Architecture -Security -Networking -Interfaces -Build Sheet (Cloud and On-premise) -Reporting -Post Migration Managed Services -Service Level Requirements | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.3 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct Functional and Technical Design Workshops and breakout sessions necessary to address and finalize requirements for migration, remediation and post-migration validation for existing custom Interface requirements for (but not limited to): -Java Programs -Encryption and Decryption, -FTP File Transfers (inbound/outbound) -File and Directory status Retrieval -SAP Vendor-Direct Interfaces for CalPERS and Bank of America -Phoenix Interface Monitor (PIM) -Interface Notifications -XML Transformations -Interface file generation and processing (inbound and outbound) -Benefit Workbench post-migration validation -Preservation of Integration History Data -Migration of Batch jobs | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.4 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct Functional and Technical Design Workshops and breakout sessions necessary to address and finalize requirements for (but not limited to): -Target Cloud Architecture -Security -Networking -Integration with Judicial Council’s Identity Management Solution (Microsoft Azure B2B) -Interfaces -Build Sheet (Cloud and On-premise) -Reporting -Post Migration Managed Services -Service Level Requirements | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.5 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct Functional and Technical Design Workshops and breakout sessions necessary to address and finalize requirements for (but not limited to): -Review of available conversion tools: --Usage Procedure Logging (UPL) --ABAP Call Monitor (SCMON) --Custom Code Lifecycle Manager (CCLM) --SAP Code Inspector --ABAP Test Cockpit (ATC) -Simplification -Addressing in the Readiness Check Dashboard -Custom Code Scoping -S/4HANA ABAP checks -Custom Code Analysis -Fit-To-Standard -Reporting -Post Migration Managed Services -Service Level Requirements | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.6 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform operational and technical assessment and analysis of the current environments for sizing and planning purposes. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.7 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop a Technical Design with supporting Build Sheets which includes: -Administrative User access (Special Requirements if any) -Application required Parameters -As-Is and To-Be Client Landscape -Availability Zones -Regions -Backup, Recovery, Retention -Complete SAP Product Build Workbook (Requires JCC input) -Connectivity for applications and Interfaces by port/protocol -Define backup schedules, retention, and policies (if applicable). -DR Planning -Finalize Platform Definitions for each Server/Application -Firewall configurations -Hardware sizing/capacity configurations -Hostnames / SID naming conventions -IP requirement, the S-User ID requirement -Network Design and Diagram -NAT Gateway Design -Server Design -Server Landscape -Software Licensing -Software Versions -Solution Manager Work Center requirements -Standardized Security Protocol definition -Storage Requirements -System User IDs / Groups -Transport Landscape | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.8 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop Migration Strategy, Plan and Schedule, optimized for TCO, which includes environment migration schedules, decommissioning plans, as-is and to-be overlapping resource costs. This includes an update of the Project Plan (12) and the Business Solution (36). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.9 | B | Migration Support, Vendor Lock-In & Exit Planning | Factor a minimum of 3 ”mock” migrations into the Migration Strategy. | 3 | Preferred | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.10 | B | Migration Support, Vendor Lock-In & Exit Planning | Update Key-Decisions Roadmap of critical decisions that will be required of key stakeholders over the course of the Project. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.11 | B | Migration Support, Vendor Lock-In & Exit Planning | Update Project Charter that outlines the scope, timeline, objectives, organization structure, project approach, high-level deliverables, resources, and governance structure. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.12 | B | Migration Support, Vendor Lock-In & Exit Planning | Optimize the final Migration Strategy contemplating the least amount of impact on production systems; ideally 0 production hours impact. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.13 | B | Migration Support, Vendor Lock-In & Exit Planning | Configure Security Groups and Setup. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.14 | B | Migration Support, Vendor Lock-In & Exit Planning | Define JCC- networks, firewalls, and connections. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.15 | B | Migration Support, Vendor Lock-In & Exit Planning | Configure VPC and Subnet. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.16 | B | Migration Support, Vendor Lock-In & Exit Planning | Confirm network Ips. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.17 | B | Migration Support, Vendor Lock-In & Exit Planning | Confirm connection set up and security. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.18 | B | Migration Support, Vendor Lock-In & Exit Planning | Address and remediate Obsolete, Not Working, Syntactic and Semantic issues with the Readiness Check Dashboard: -Active Business Functions -Add-On Compatibility -Business Process Analytics -Business Warehouse Extractors -Custom Code Analysis -Data Volume Management -HANA Sizing -Simplification Items | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.19 | B | Migration Support, Vendor Lock-In & Exit Planning | Rerun Readiness Check as needed until all flagged items are corrected. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.20 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform System Builds using the Build Sheets and workbook developed earlier: -AD and DNS Setup -Build VM’s per Build Sheet -Create repeatable VM images -Configure backups to support SLAs -Configure HA and DR setup -Configure the SAP HANA database and applications -Create templates for new VMs or VMs from source/deployment automation -DR Provision and Configuration -Execute technical cutover (final data/networking) -HA Provision and Configuration -Migrate data / VM source files for testing -Set up NAT Gateway Address Translation Tables -Network, Storage, and Compute Provisioning -OS/DB/Infra hardening per JCC-defined STIGs -Replicate data for production cutover -Setup DB monitoring -Setup Infrastructure monitoring -Setup OS monitoring -Troubleshoot application issues -Troubleshoot infrastructure issues -Update Documentation - Build Sheets, STIG, Gold Image doc, Low-Level Design document, High-Level Design Document as needed -Workload planning and stress testing (if applicable) | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.21 | B | Migration Support, Vendor Lock-In & Exit Planning | Deploy Operating Systems and Database(s): -Provision virtual machine with operating systems -Create operating system backups -Install and configure OS Libraries -OS Parameters for Specific SAP Build Installs -Apply SAP Best Practices / Azure specific OSS Notes -Apply SAP specific OSS Notes related to target Cloud Services Provider -OS Monitoring Agent Configuration -OS Backup Agent Configuration -Windows Active Directory Configuration -Configure OS for Network Configuration -Provide LDAP / AD user accounts -Provide DNS entries cloud -Add Cloud AD to JCC AD or Cloud systems to JCC AD -Define System (Privileged) Accounts and groups to be created -Define the operating system STIGs -Implement OS STIGs -Configure NTP server in accordance with agreed-upon settings -Define the appropriate time zone on a per-server basis and provide the time zone server URL. -Provision/Install DB -Configure Table Spaces -Create and Maintain Custom DB Objects -Configure Backup, Restore and Recovery -Install initial OS and DB Patches -Install and Configure DB tools -Install and Configure 3rd party tools | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.22 | B | Migration Support, Vendor Lock-In & Exit Planning | Act as the primary point of contact with the JCC Customer-Facing Business Team. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.10.1.23 | B | Migration Support, Vendor Lock-In & Exit Planning | Work with JCC partners, owners of external systems, and/or third-party service providers to collect information required to develop and document a detailed interface design and approach (in the Detailed Design Standards and Design Documents) according to JCC standards. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.24 | B | Migration Support, Vendor Lock-In & Exit Planning | Document the Technical System Design specifying all components, modules, data stores, reports, interfaces, interface components (e.g. Axway and direct), Bidder-Proposed Enterprise Technology Tools, and associated operations procedures for the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.25 | B | Migration Support, Vendor Lock-In & Exit Planning | Review and approve detailed design documentation. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.10.1.26 | B | Migration Support, Vendor Lock-In & Exit Planning | Create/document Unit, Integration, End-to-End, User Acceptance, Document Conversion, Regression, and Security Test Plans. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.27 | B | Migration Support, Vendor Lock-In & Exit Planning | Create test environments necessary to support the ongoing application development/configuration including any elements required for supporting the enhanced functions or features. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.28 | B | Migration Support, Vendor Lock-In & Exit Planning | Install Bidder-Proposed Enterprise Technology Tools (and any other utilities/tools if required to support the Bidder's methodology) in the test environments necessary to support the ongoing application development/configuration including any elements required for performance testing and validation, or which support enhanced functions or features. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.29 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide all Test Plans and Test Scripts in alignment with the Master Test Strategy. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.10.1.30 | B | Migration Support, Vendor Lock-In & Exit Planning | Establish formal Response Time and Capacity Testing Strategy and Plans. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.31 | B | Migration Support, Vendor Lock-In & Exit Planning | Establish, document, remediate, and maintain the overall Reports, Interfaces, Conversions, Enhancements and Workflows, Development Schedule. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.32 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide training materials for initial training and knowledge transfer to the JCC support organization. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.33 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide initial training and knowledge transfer to the support organization, in accordance with the Training and Knowledge Transfer Plan, to support the detailed requirements definition phase of implementation activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.34 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Training Curriculum Document that outlines the training and course content including the course topics and the content to be delivered with each topic. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.10.1.35 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide formal End-user Training Strategy and Plans to document training requirements and the approach the JCC will use for updating training requirements, development of training curricula, and deploying training for the end-users as required. Include training milestones with clear deliverables for each set of activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>

## 2.11.1 Realize
RQM-ID | Category Code | Category of Requirements | Requirement Description | Priority # | Priority | SubType Category | Req Type Classification | Vendor | JCC | SoH | S/4 | Vendor Response Code | Vendor Response Category | Vendor Response Comments | RL
2.11.1.1 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform all necessary technical design, development, configuration, document conversion/migration, unit testing, and scripting, of system modules as required to provide and implement the design specifications. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.2 | B | Migration Support, Vendor Lock-In & Exit Planning | Create Test Cases and Test Data that are fully documented and repeatable without consulting assistance. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.11.1.3 | B | Migration Support, Vendor Lock-In & Exit Planning | Create a test environment and documents where required by the project, including a demonstration of requirements traceability to verify the requirements as specified in the requirements document have been satisfied. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.4 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Data Transfer services, separate from the Cloud Services Provider, including media and courier services, to transfer on-premise production data to the Cloud Service Provider in a manner that meets the “mock“ cutover SLA. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.5 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct all appropriate testing (e.g. unit testing, end-to-end testing, response time and capacity testing, regression testing, parallel testing). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.6 | B | Migration Support, Vendor Lock-In & Exit Planning | Complete Functional Adaptation: -Rerun checks for HANA compatibility e.g. using ATC -Update modifications to standard transactions SPDD, SPAU, SPAU_ENH -Fix S/4HANA Findings -Review Simplification Items -Run ABAP SQL Monitor -Tune for performance | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.7 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide and document test results, Documented Successful Testing Results. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.11.1.8 | B | Migration Support, Vendor Lock-In & Exit Planning | Validate the system for compliance with the System Security Strategy and Plans. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.9 | B | Migration Support, Vendor Lock-In & Exit Planning | Manage the JCC functional, integration, parallel, and regression test environments and associated test data including creation and maintenance during the testing period. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.10 | B | Migration Support, Vendor Lock-In & Exit Planning | Review testing results for compliance with policies, procedures, plans, and test criteria and metrics (e.g. defect rates, progress against schedule). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.11.1.11 | B | Migration Support, Vendor Lock-In & Exit Planning | Coordinate user acceptance testing (e.g. gain user involvement, establish and define acceptance criteria, setting high-level test objectives, establish high-level test scenarios, establish end-to-end test scenarios). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.11.1.12 | B | Migration Support, Vendor Lock-In & Exit Planning | Facilitate and support user acceptance test as prescribed by the JCC, including: establishing adequate test environment based on user acceptance criteria; preparing data to support test scenarios within modified system as well as managing the relationship with all interfaced systems necessary to conduct test; troubleshooting; supporting users to progress through scenarios; simulating interfaces or working with integrated systems to conduct end-to-end tests; supporting document batch/load processing; exercising functionality; and reporting results. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.11.1.13 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct user acceptance tests. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.14 | B | Migration Support, Vendor Lock-In & Exit Planning | Utilize the JCC-preferred defect tracking tool (ServiceNow). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.15 | B | Migration Support, Vendor Lock-In & Exit Planning | Correct defects found as a result of testing efforts. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.16 | B | Migration Support, Vendor Lock-In & Exit Planning | Review and approve configuration management policies and procedures. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.11.1.17 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform configuration management activities throughout the life cycle. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.18 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide training materials to support end-user training. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.19 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform Organizational Readiness Assessment to identify opportunities and resistance to changes. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.20 | B | Migration Support, Vendor Lock-In & Exit Planning | Create and maintain the JCC training data as required by the JCC. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.21 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Training and Knowledge Transfer Effectiveness Reports for the JCC support organization. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.11.1.22 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide and apply appropriate business process and organizational change management tools and activities while ensuring processes are in place for communication. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>

## 2.12.1 Final Preparation
RQM-ID | Category Code | Category of Requirements | Requirement Description | Priority # | Priority | SubType Category | Req Type Classification | Vendor | JCC | SoH | S/4 | Vendor Response Code | Vendor Response Category | Vendor Response Comments | FP
2.12.1.1 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Initial and Final Deployment Plans (turn-over-to-production plan). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.12.1.2 | B | Migration Support, Vendor Lock-In & Exit Planning | Coordinate deployment and support activities with applicable JCC sites. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.3 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform deployment and support activities with applicable JCC sites. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.4 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct pre-installation business surveys to assess site readiness against a set of best practices checklist criteria. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.5 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop Transition Plans that encompass business process, operations (business and IT), and technical-support plans that need to be in place to mitigate implementation risk. Coordinate this documentation with site-specific end-user training activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.6 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Recommended Operations and Administration Procedures related to the deployment. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.7 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Role to Position Mapping Document which outlines the security roles, positions, and authorizations configured in the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.8 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a mechanism for JCC representatives to review and accept converted/migrated data elements before production deployment of new or upgraded functionality. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.12.1.9 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Data Transfer services, separate from the Cloud Services Provider, including media and courier services, to transfer on-premise production data to the Cloud Service Provider in a manner that meets the cutover SLA. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.10 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform final migration from existing system(s) to the Phoenix system, by electronic or manual methods and perform selected integration, response time and capacity, end-to-end, and user-acceptance testing to validate that the solution is ready for production. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.12.1.11 | B | Migration Support, Vendor Lock-In & Exit Planning | Track deployment and document migration/conversion status and notification. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.12 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Training and Knowledge Transfer, in support of developing a Level 2 support team to the JCC support personnel, prior to deployment. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.12.1.13 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide training materials, including dialogue scripts, for Level 2 support for the system to the JCC and other vendor personnel as applicable. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.14 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop/provide Technical Documentation as well as training related to configuration management, installation, development and performance tuning for targeted JCC technical and functional personnel. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.15 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop business process support documentation and associated business rules and configuration parameters for the targeted JCC project team and business super users. Deliver the “train the trainer” training. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.16 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide initial Operational End-user Training for the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.17 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Draft and Final End-user Training Materials for the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.12.1.18 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide communications materials and Site-specific Training Materials. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.19 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide recommendations for ongoing business process and organizational change management activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.20 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Post Production Support Strategy which outlines the processes for end-users to obtain support in the post-go-live environment. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.12.1.21 | B | Migration Support, Vendor Lock-In & Exit Planning | Implement business process and organizational change management recommendations. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.22 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide formal Business Continuity Strategy and Plans that describe the approach that will be taken to adhere to SLRs and perform business disaster recovery activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.23 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide formal Managed Services Support Strategy and Plans that describe the approach that will be taken to perform business ongoing support activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.12.1.24 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide updated monthly costs for Managed Services for 1-year and 3-year (hosting commitment) terms. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Informed | Responsible |  |  | <select>
2.12.1.25 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide updated monthly costs for Managed Services. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Informed | Responsible |  |  | <select>
2.12.1.26 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide a Business Contingency Plan that describes the approach that will be taken during go-live activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.27 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Batch Schedule which sequences the execution of automated background jobs for processing with other JCC production jobs. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.28 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide metrics regarding scalable and acceptable levels of performance. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.29 | B | Migration Support, Vendor Lock-In & Exit Planning | Update the training and knowledge transfer plan as required. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.30 | B | Migration Support, Vendor Lock-In & Exit Planning | Develop help desk scripts. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.31 | B | Migration Support, Vendor Lock-In & Exit Planning | Create a Go/No-go Checklist. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.12.1.32 | B | Migration Support, Vendor Lock-In & Exit Planning | Approve production deployment go/no-go decisions. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select>
2.12.1.33 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct Go/No-go Meeting and develop Go/No-go Documentation. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y

## 2.13.1 Go-Live
RQM-ID | Category Code | Category of Requirements | Requirement Description | Priority # | Priority | SubType Category | Req Type Classification | Vendor | JCC | SoH | S/4 | Vendor Response Code | Vendor Response Category | Vendor Response Comments | GL
2.13.1.1 | B | Migration Support, Vendor Lock-In & Exit Planning | Successfully meet all Section 1.3 Fundamental and ensure Acceptance by the JCC. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.2 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide 12 months of post-implementation warranty support which is exclusive of any additional responsibilities of the JCC’s Managed Services and Ongoing Operational Support provider. | 2 | Highly Desirable | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.3 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide monthly reports detailing the warranty work (i.e., number and type of defects, the status of defects). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.4 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform system fixes to correct system-level performance problems that the Bidder was responsible for. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.5 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform additional custom code remediation as identified as warranty work. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.6 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform fixes to correct improperly converted files or tables that the Bidder was responsible for. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.7 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform fixes to correct translation or load errors for interfaces that the Bidder was responsible for. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.8 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform fixes to correct errors from application configuration or parameter table settings that are not consistent with the intended design and were the responsibility of the Bidder. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.9 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform training fixes to correct interpretation and documentation errors related to the user or technical training documentation or other training delivery media developed by the Bidder. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.10 | B | Migration Support, Vendor Lock-In & Exit Planning | Test the system to ensure that no regression errors are introduced. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.11 | B | Migration Support, Vendor Lock-In & Exit Planning | Approve of all Warranty Service fixes with formal sign-off. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.12 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide operating system support. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.13 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide monitoring and tuning for performance and backup. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.14 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct active performance monitoring. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.15 | B | Migration Support, Vendor Lock-In & Exit Planning | Update all documentation and related files/deliverables such as: -Business Solution documents. -Requirements Definition documents. -Design and Specification documents. -Workflows, Reports, Interfaces, Conversion/Migration, and Enhancements functional and technical specifications. -Package Configuration and Development documents as well as any associated system changes. -Integration and Testing documents as well as test data/documents. -Implementation and Migration Deployment documents. -Problem Monitoring and Reporting documents. -Change Control documents and associated configuration parameters and system source code. -Training documents and associated training data. -Knowledge Transfer documents. -Operational support processes and procedures. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.16 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct and document an Organizational Change Management Effectiveness Assessment. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.17 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform system administration, if required. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.18 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform software configuration, if required. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.19 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform software customization, if required. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.20 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform report development (as requested per approved change order). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.21 | B | Migration Support, Vendor Lock-In & Exit Planning | Monitor and tune the system for performance. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.22 | B | Migration Support, Vendor Lock-In & Exit Planning | Execute and maintain the Business Continuity Plan. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.23 | B | Migration Support, Vendor Lock-In & Exit Planning | Maintain Level help desk scripts. | 1 | Mandatory | 1.7.10.13 Help Desk | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.24 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct ongoing operations end-user training. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.25 | B | Migration Support, Vendor Lock-In & Exit Planning | Install new or enhanced software functions or features. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.26 | B | Migration Support, Vendor Lock-In & Exit Planning | Participate in an ongoing review of Phoenix architecture and recommend any modifications to architecture design as it may relate to the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.27 | B | Migration Support, Vendor Lock-In & Exit Planning | Refine, configure and maintain high-level release-specific system architectures. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.28 | B | Migration Support, Vendor Lock-In & Exit Planning | Maintain “End State” system architecture. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.29 | B | Migration Support, Vendor Lock-In & Exit Planning | Document/create Maintenance and Repair Policies and Procedures. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.30 | B | Migration Support, Vendor Lock-In & Exit Planning | Document/create a System Maintenance Plan (e.g. committed and proposed work schedules). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.31 | B | Migration Support, Vendor Lock-In & Exit Planning | Maintain all revisions to the plan (e.g. committed and proposed work schedules). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.32 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide system maintenance plan for all categories of maintenance services (e.g. Minor Enhancements, Corrective Maintenance, Preventative Maintenance, Adaptive Maintenance, and Perfective Maintenance) as described above. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.33 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide technical and functional support to the JCC as directed by the JCC. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.34 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide business hours and off-hours Go live and Deployment support. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.35 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform Warranty diagnostics on software and services. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.36 | B | Migration Support, Vendor Lock-In & Exit Planning | Recommend Warranty database management system tuning changes. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.37 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Level 1 help desk with coordination of user support activities (including “how to” support and user account and password administration). | 1 | Mandatory | 1.7.10.13 Help Desk | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.38 | B | Migration Support, Vendor Lock-In & Exit Planning | Respond to escalated trouble ticket items in accordance with established procedures. | 1 | Mandatory | 1.7.10.4 Incident Resolution | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.39 | B | Migration Support, Vendor Lock-In & Exit Planning | Establish priority of trouble ticket items/service requests. | 1 | Mandatory | 1.7.10.4 Incident Resolution | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.40 | B | Migration Support, Vendor Lock-In & Exit Planning | Approve and sign-off on all site-specific migrated data. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.41 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide on-site implementation support. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.42 | B | Migration Support, Vendor Lock-In & Exit Planning | Conduct post-implementation acceptance tests and provide results. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.43 | B | Migration Support, Vendor Lock-In & Exit Planning | Review/approve post-implementation acceptance test results. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.44 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Maintenance Production Release Plans and schedules. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.45 | B | Migration Support, Vendor Lock-In & Exit Planning | Participate in scheduling releases (e.g. upgrades and/or ongoing configuration changes). | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.46 | B | Migration Support, Vendor Lock-In & Exit Planning | Review configuration management results. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Supports | Responsible |  |  | <select> |  |  | Y
2.13.1.47 | B | Migration Support, Vendor Lock-In & Exit Planning | Recommend and document processes and procedures associated with change requests. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.48 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide ongoing end-user training for improving “how-to-use” skills related to the system. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.49 | B | Migration Support, Vendor Lock-In & Exit Planning | Assess the effectiveness of the business process and organizational change management activities. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select>
2.13.1.50 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide Roadmap for the Deployment of subsequent initiatives. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.51 | B | Migration Support, Vendor Lock-In & Exit Planning | Document Successful Deployment. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.52 | B | Migration Support, Vendor Lock-In & Exit Planning | Perform Phase Closeout including system tuning activities, assessment of knowledge transfer tasks, transfer project artifacts to project repository, lessons learned document, update Business Solution, and transition support to COE and/or Shared Services organization. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.53 | B | Migration Support, Vendor Lock-In & Exit Planning | Warranty Services will be provided pursuant to final acceptance as stipulated in the contract. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y
2.13.1.54 | B | Migration Support, Vendor Lock-In & Exit Planning | Provide and perform orderly handover of processes and procedures for tracking and reporting the status of all warranty services. | 1 | Mandatory | 1.7.15.2.13 Management and DevOps | Migration & Integration | Responsible | Supports |  |  | <select> |  |  | Y