## Summary
1.0 Implementation and Deployment Services Overview
This Exhibit 2 (Implementation and Deployment Services Requirements) are the requirements that set forth the roles and responsibilities of the parties for the DR Implementation and Deployment Services to be provided. These are the services required to devise a well thought out and thorough approach, a standards and best practices based methodology and deployment plan, and a successful deployment of the DR Services. The Implementation and Deployment Services shall include, but are not limited to the following: • Preliminary Discovery & Analysis Services • Solution Design and Implementation Planning Services • Infrastructure Implementation in the Cloud • Application configuration and DR Deployment • Simulation DR and Failback • Testing Services • Project Management Services • Training and Knowledge Transfer
Instructions: Tab 2 Implementation & Deployment Services - Please provide response to the questions. The proposer may attach any additional pages required to fully address any of the requirements, provided each addition page is clearly labeled with the requirement number and category name/description to which it applies.

## Deployment - Requirements
# | Priority | Category | Requirement Text | Yes/No | Vendor Response | Notes / Comments
1 | Mandatory | Deployment | Professional Services resources meet Silver and/or gold level - Cloud Platform competency, Datacenter competency, and DevOps competency
2 | Mandatory | Deployment | Provide details on proposer's role in managing operations failback from the cloud data center back to JBE’s production data center.
3 | Mandatory | Deployment | Provide details on the extent which the offeror trains the customer’s support staff in the use and management of the DR Solution and related services.
4 | Mandatory | Deployment | Provide discovery services on JBE environment. Discovery shall include but not be limited to: • Application and Service Dependency Mapping • Logical Data Connections Analysis • Data Center Configuration Analysis • Data Network Analysis • Data Storage and Replication Analysis • End State Requirements for all services (infrastructure, compute, network, data) identifying options and applicable cloud vendor service offerings.
5 | Mandatory | Deployment | Decribe the methodology used to perform discovery and analysis sevices to record technology assests and identify Disaster Recovery end state requirements to enable creation of an implementation strategy and approach
6 | Mandatory | Deployment | Describe your implementation planning process
7 | Mandatory | Deployment | List the post implementation documentation will be provided and include detailed system configurations, settings and modifications, and details on items requiring routine periodic modifications.
8 | Mandatory | Deployment | Provide details on project management services for each implementation including the development of and updates to a work breakdown structure and staff schedueling plan, issue and risk management, status calls and reports.
9 | Mandatory | Deployment | Vendor will create a playbook and design solution templates with prerequisites for deployment of an application or service recovery using the proposers solution
10 | Mandatory | Deployment | Documentation and checklist should be created for each service covering failover and fail back procedures, expected RTO/RPO,
11 | Mandatory | Deployment | The solution will allow for JBE to unilaterally deploy configuration changes once the DR infrastructure has been provisioned
12 | Mandatory | Deployment | Describe your recommendation for roles your company personnel will assume and the roles that Court staff should assume in the implementation process.
13 | Mandatory | Deployment | Describe the designs service offerings to extend local infrastructure services to the cloud
14 | Mandatory | Deployment | Describe the designs service offerings for provisioning recovery solution for applications and systems using cloud services
15 | Mandatory | Deployment | Describe the on-premise backup and infrastructure requirements and how the proposers solution will leverage existing backup, ,archival and other technologies used in the Courts
16 | Mandatory | Deployment | Describe your process for coordinating software upgrades and version management for proposed solution
17 | Mandatory | Deployment | Describe your implementation approach for • Connectivity Security • Data and Confguration replication • Scripting and sequencing for automated deployments • Post deployment scenario testing • Failover and Failback process
18 | Mandatory | Deployment | Describe how the solution will be monitored for performance and security. List the requirements and monitoring tools proposed and details on how logs are managed and reporting features.