## Target-GMP-Breakdown
Target GMP/GMP Preparation Form
Project Description: |  | P27-J-01 New Fort Ord Courthouse - #220 - #224 - Revised Site |  |  | Con Start JCC | 2026-01-01 |  | Con Start TGMP |  |  | Final Con Start
Project Type: |  | Courthouse |  |  | Con Comp JCC | 2028-04-01 |  | Con Comp TGMP |  |  | Final Con Comp
Location |  | Salinas
Gross Building Area:(GSF) |  | 83000 | Per JCC Budget |  |  |  |  | Based on JCC Area | 83000 |  | GBA GSF
2022-12-01 |  | 8823 | CCCI @ Midpoint | 11408 | JCC TGMP COSTS |  |  | DBE TGMP COSTS |  |  | DBE GMP COSTS
|  |  |  | UNIFORMAT | TOTAL | COST PER | % OF | TOTAL | COST PER | % OF | TOTAL | COST PER | % OF
SYSTEM / ELEMENT DESCRIPTION |  |  |  | REF # | COST | GSF | DIRECT COST | COST | GSF | DIRECT COST | COST | GSF | DIRECT COST
BUILDING:
1 | Foundations - Standard |  |  | (A1010) | 2141898 | 25.806 | 2.11% |  | 0 | 0% |  | 0 | 0%
2 | Foundations - Other |  |  | (A1020) | 295463.4 | 3.5598 | 0.2911% |  | 0 | 0% |  | 0 | 0%
3 | Foundations - Slab on Grade |  |  | (A1030) | 1373185.2 | 16.5444 | 1.353% |  | 0 | 0% |  | 0 | 0%
4 | Basement / Secure Parking |  |  | (A20) | 0 | 0 | 0% |  | 0 | 0% |  | 0 | 0%
5 |  | Substructure - Sub-Total |  | (A) | 3810546.6 | 45.9102 | 3.754% | 0 | 0 | 0% | 0 | 0 | 0%
6 | Superstructure |  |  | (B10) | 12442480.2 | 149.9094 | 12.26% |  | 0 | 0% |  | 0 | 0%
7 | Exterior Enclosure |  |  | (B20) | 10684938.6 | 128.7342 | 10.53% |  | 0 | 0% |  | 0 | 0%
8 | Roofing |  |  | (B30) | 2250262.8 | 27.1116 | 2.217% |  | 0 | 0% |  | 0 | 0%
9 |  | Shell - Sub-Total |  | (B) | 25377681.6 | 305.7552 | 25% | 0 | 0 | 0% | 0 | 0 | 0%
10 | Interior Construction |  |  | (C10) | 14760471 | 177.837 | 14.54% |  | 0 | 0% |  | 0 | 0%
11 | Stairs |  |  | (C20) | 703524.6 | 8.4762 | 0.6932% |  | 0 | 0% |  | 0 | 0%
12 | Interior Finishes |  |  | (C30) | 7175781.6 | 86.4552 | 7.07% |  | 0 | 0% |  | 0 | 0%
13 |  | Interiors - Sub-Total |  | (C) | 22639777.2 | 272.7684 | 22.31% | 0 | 0 | 0% | 0 | 0 | 0%
14 | Conveying Systems |  |  | (D10) | 2263808.4 | 27.2748 | 2.23% |  | 0 | 0% |  | 0 | 0%
15 | Plumbing |  |  | (D20) | 3096862.8 | 37.3116 | 3.051% |  | 0 | 0% |  | 0 | 0%
16 | HVAC |  |  | (D30) | 8355942 | 100.674 | 8.233% |  | 0 | 0% |  | 0 | 0%
17 | Fire Protection |  |  | (D40) | 1403662.8 | 16.9116 | 1.383% |  | 0 | 0% |  | 0 | 0%
18 | Electrical - Service & Distribution |  |  | (D5010) | 3037600.8 | 36.5976 | 2.993% |  | 0 | 0% |  | 0 | 0%
19 | Electrical - Solar Panels |  |  | (D5010.30) | 2005353 | 24.1609 | 1.976% |  | 0 | 0% |  | 0 | 0%
20 | Electrical - Lighting & Branch Wiring |  |  | (D5020) | 4470048 | 53.856 | 4.404% |  | 0 | 0% |  | 0 | 0%
21 | Electrical - Communications & Security |  |  | (D5030) | 5269238.4 | 63.4848 | 5.192% |  | 0 | 0% |  | 0 | 0%
22 | Electrical - Other Systems |  |  | (D5040) | 2456833.2 | 29.6004 | 2.421% |  | 0 | 0% |  | 0 | 0%
23 |  | Services - Sub-Total |  | (D) | 32359349.4 | 389.8717 | 31.88% | 0 | 0 | 0% | 0 | 0 | 0%
24 | Equipment |  |  | (E10) | 2214705.6 | 26.6832 | 2.182% |  | 0 | 0% |  | 0 | 0%
25 | Furnishings |  |  | (E20) | 2017447.8 | 24.3066 | 1.988% |  | 0 | 0% |  | 0 | 0%
26 | Special Construction |  |  | (F) | 0 | 0 | 0% |  | 0 | 0% |  | 0 | 0%
27 | SUBTOTAL BUILDING |  |  | (SB) | 88419508.2 | 1065.2953 | 87.12% | 0 | 0 | 0% | 0 | 0 | 0%
SITE:
28 | Site Preparation |  |  | (G10) | 1423794.54 | 17.1542 | 1.403% |  | 0 | 0% |  | 0 | 0%
29 | Site Improvements |  |  | (G20) | 3077395.08 | 37.077 | 3.032% |  | 0 | 0% |  | 0 | 0%
30 | Site Mechanical Utilities |  |  | (G30) | 292903.2 | 3.529 | 0.2886% |  | 0 | 0% |  | 0 | 0%
31 | Site Electrical Utilities |  |  | (G40) | 528143.76 | 6.3632 | 0.5204% |  | 0 | 0% |  | 0 | 0%
32 | Other Site Construction |  |  | (G50) | 4798307.1 | 57.8109 | 4.728% |  | 0 | 0% |  | 0 | 0%
33 | SUBTOTAL SITEWORK & UTILITIES: |  |  | (G) | 10120543.68 | 121.9343 | 9.971% | 0 | 0 | 0% | 0 | 0 | 0%
34 | SUBTOTAL BUILDING & SITEWORK |  |  | SB+(G) | 98540051.88 | 1187.2295 | 97.09% | 0 | 0 | 0% | 0 | 0 | 0%
35 | Project Contingency |  |  | 3% | 2956201.5564 | 35.6169 | 2.913% |  | 0 | 0% |  | 0 | 0%
36 | (E&O - Note: included in trade costs) |  |  | 2% | incl. |  |  | incl. |  |  | incl.
37 | Escalation to Midpoint |  |  | 17.46% | incl. |  |  | incl. |  |  | incl.
38 | Allowances per JCC |  |  |  | 0 | 0 | 0% |  | 0 | 0% |  | 0 | 0%
39 | Additional Allowances |  |  |  | 0 | 0 | 0% |  | 0 | 0% |  | 0 | 0%
40 | TOTAL DIRECT COST OF THE WORK |  |  |  | 101496253.4364 | 1222.8464 | 100% | 0 | 0 | 0% | 0 | 0 | 0%
CONSTRUCTION SERVICES
41 | Construction Administration- AE (C1) |  |  |  | 1319451.2947 | 15.897 | 1.3% |  | 0 | 0% |  | 0 | 0%
42 | General Conditions - Staff/Other (C2 & C3) |  |  |  | 8525685.2887 | 102.7191 | 8.4% |  | 0 | 0% |  | 0 | 0%
43 | Bonds (C4) |  |  |  | 1116458.7878 | 13.4513 | 1.1% |  | 0 | 0% |  | 0 | 0%
44 | Insurance (non-OCIP if applicable) (C5) |  |  |  | 507481.2672 | 6.1142 | 0.5% |  | 0 | 0% |  | 0 | 0%
45 | Construction Fee (OH&P) (C6) |  |  |  | 5785286.4459 | 69.7022 | 5.7% |  | 0 | 0% |  | 0 | 0%
46 | Construction Fees and Services Subtotal |  |  |  | 17254363.0842 | 207.8839 | 17% | 0 | 0 | 0% | 0 | 0 | 0%
47 | TGMP (GMP) Total |  |  |  | 118750616.5206 | 1430.7303 | 117% | 0 | 0 | 0% | 0 | 0 | 0%