Development Scope, Deliverable, and Acceptance Criteria

| # | Title | Description | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 1 | Review Artifacts and Update Architecture Design | - Review all project artifacts including requirements, designs, diagrams, test plans, proofs of concept results, build plan, etc. - Compare Architecture Design document to Requirements and Functional documentation and identify any gaps or issues - Review new requirements and update Architecture Design document with solutions to new requirements | - Gap analysis of requirements to design - Updated Architecture Design document - Facilitate a walkthrough of the updated Architecture Design document with the AOC technical team; update as necessary - Timeframe: July, 2009 | The AOC Project Manager approves deliverables of gap analysis and updated Architecture Design document |
| 2 | Test Case Development | - Create comprehensive test plan that covers functional, regression, integration and performance consistent with the guidelines described in the AOC Test Strategy Best Practices (July 2006). - Develop test script based upon traceability to the Requirements and Architecture Design documentation, using ISB standard templates. | - Comprehensive Test Plan - Test scripts and results covering all functional, regression, integration and performance cases - Facilitate a walkthrough of completed Test cases document. - Facilitate a walkthrough of completed Test Plan. - Timeframe: July, 2009 | The AOC Project Manager approves deliverables of Test Plan and scripts |
| 3 | Development and Functional Components Demonstration | - Create proof of concepts as they relate to integration with other components including FileNet P8 CE, DataMaxx/CLETS, and Web Service users including CCMS and local court data repositories - Configure TIBCO products per Architecture Design documentation. - Design and document web services integration specification for CCMS and external court users, including ETL functions - Unit test configurations in the AOC development environment, or alternate environment as designated by the AOC. | - Demonstration of results from proof of concepts - Demonstration to stakeholders of the related functional components and exception cases, including a walk through of configured processes. - Provided detailed list of error messages for review during the demonstration. - Facilitate components demonstration to stakeholders as designated by the AOC, including internal technical staff, court technical analysts, and CCTC environment support staff. - Timeframe: July – August, 2009 | The AOC Project Manager approves deliverables of functional components demonstration consistent with requirements and design |
| 4 | Deployment Guide Development | - Review the ISB standard Deployment Guide template. - Prepare Deployment guide document using the ISB template. | - Deployment guide for use by Data Center resources within CCTC pre-production environments, including at a minimum: - TIBCO component descriptions, locations and dependencies - Promotion procedures for the new services. - Timeframe: July – August, 2009 | The AOC Project Manager finds that the ISB Deployment guide includes the information in the Deliverable Description. |
| 5 | Test Results and Deployment | Work with teams to: - Deploy the configurations into the CCTC TEST and STAGING environments. - Execute tests in accordance with the test plan and cases, and document results. - Review results with Teams stakeholders for approval. - Prepare Test results document. - Facilitate a walkthrough of completed Test results document. | - Performs functional, regression, integration and performance testing of TIBCO deliverables. - Documented test results based on execution of the test plan, with 100% tests completed unless deferred or removed with approval by the participants identified for this Deliverable in the RAM. - Timeframe: September, 2009 | The AOC Project Manager finds that the Test results document includes the information in the Deliverable Description, and map to the test categories defined in the Test Plan. |
| 6 | UAT assistance | - Participate in the User Acceptance Testing (UAT) phase at the direction of the AOC Project Manager. - Provide weekly input to the AOC Project Manager on UAT issues to be reviewed on a monthly basis. | - Participates in the UAT phase at the direction of the AOC Project Manager. - Provide weekly input to the AOC Project Manager on UAT issues to be reviewed on a monthly basis. - Timeframe: November, 2009 |  |
| 7 | Deployment assistance | - Participate in deployment of CCPOR Pilot for a court at the direction of the AOC Project Manager. - Review pilot courts designs, address web services specification requirements, and provide integration test support. | - Participates in the pilot court onboarding activities at the direction of the AOC Project Manager. - Timeframe: December 2009 – March, 2010 |  |
| 8 | Project Management | - Prepare and distribute weekly status reports, including monthly financials summary. - Participate in project monitoring, control and governance activities. | - Weekly Status Report Summary - Monthly budget report, including travel expenses up to 30-days from date expense was incurred. - Timeframe: Ongoing |  |
| 9 | Project Closure | - Facilitate lessons learned discussions. - Recommend action plan for possible future work. - Document project summary, including summary of activities and financials for the project, open issues, reusability components and input for ISB best practices updates. | - Project review documentation includes: - Project description - TIBCO PortalBuilder component design. - Application component design. - Lessons learned summary. - Test results summary. - Service hours and financial summary. - Suggestions for possible future enhancements. - Recommended reusable components that may be applied to future similar projects. - Feedback to the AOC regarding prospective changes or enhancements to ISB best practices. - Timeframe: March 2010 | The AOC Project Manager finds that the Project review documentation includes the information in the Deliverable Description. |

End of Appendix A