## SB 1732 group
General Funded Capital Projects - Active
a | b | c | d |  | e | f | g | h | i | j
Estimated Schedule1
# | Initial Year Authorized | County | Project Name |  | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Costs2
1 | 07-08 | Los Angeles | New Long Beach Courthouse | Acquisition close to finish; currently in finishing SD, | In Acquisition | Fall 2009 | Fall 2010 | Summer 2010 | Fall 2012 | 296635000
[9 empty] | Total (2): | 296635000
SB 1732 Capital Projects - Active
a | b | c | d |  | e | f | g | h | i | j
Estimated Schedule1
# | Initial Year Authorized | County | Project Name |  | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Costs2
1 | 07-08 | Calaveras | New San Andreas Courthouse | Preliminary Plans | In Design | Completed | Fall 2010 | Fall 2010 | Spring 2012 | 43579000
2 | 05-06 | Contra Costa | New Antioch Area Courthouse | Construction | In Construction | Completed | Completed | Spring 2009 | Fall 2010 | 64729000
3 | 06-07 | Fresno | BF Sisk Conversion | Construction | In Construction | Completed | Completed | Summer 2008 | Fall 2010 | 70898000
4 | 07-08 | Lassen | New Susanville Courthouse | Working Drawings | In Design | Completed | Spring 2010 | Summer 2010 | Fall 2011 | 38937000
5 | 07-08 | Madera | New Madera Courthouse | Acquisition/Preliminary Plans | In Acquisition and design has been authorized | Winter 2010 | Summer 2011 | Summer 2011 | Spring 2013 | 97815000
6 | 06-07 | Mono | New Mammoth Lakes Courthouse | Working Drawings | In Design | Completed | Winter 2010 | Winter 2010 | Summer 2011 | 21522000
7 | 06-07 | Plumas/Sierra | New Portola/Loyalton Courthouse | Construction | Completed | Completed | Completed | Completed | Completed | 6496000
8 | 07-08 | Riverside | New Mid-County Courthouse | Preliminary Plans | In Design | Completed | Fall 2010 | Fall 2010 | Summer 2012 | 63507000
9 | 07-08 | San Benito | New Hollister Courthouse | Preliminary Plans | In Design | Completed | Winter 2011 | Winter 2011 | Summer 2012 | 36156000
10 | 07-08 | San Bernardino | New San Bernardino Courthouse | Preliminary Plans | In Design | Completed | Winter 2011 | Winter 2011 | Winter 2013 | 341905000
11 | 07-08 | San Joaquin | New Stockton Courthouse | Preliminary Plans | In Design | Completed | Summer 2011 | Summer 2011 | Summer 2013 | 261979000
12 | 07-08 | Tulare | New Porterville Courthouse | Preliminary Plans | In Design | Completed | Summer 2011 | Summer 2011 | Winter 2013 | 91902000
[9 empty] | Total (3): | 1139425000
[9 empty] | Total of active capital projects (subtotal 2 + 3): | 1436060000
[9 empty] | Total (subtotal 1+2+3): | #VALUE!
Notes:
1. Current estimated project schedules and may change.
2. Current total estimated project costs and may change.

## SB 1732 group (old) (hidden)
Completed Capital Projects
a | b | c | d |  | e | f | g | h | i | j | k
Estimated Schedule
# | Initial Year Authorized | County | Project Name | Current Project Phase | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
1 |  | Fresno | Court of Appeal, Fifth Appellate District | Completed | Completed and Occupied | Completed | Completed | Completed | Completed | 20300000 | Completed
2 |  | Merced | New Merced Downtown Courthouse | Completed | Completed and Occupied | Completed | Completed | Completed | Completed | 19700000 | Completed
3 |  | Fresno | New Fresno Area Juvenile Delinquency Courthouse | Completed | Completed and Occupied | Completed | Completed | Completed | Completed | 57900000 | Completed
4 |  | Orange | Court of Appeal, Fourth Appellate District Division 3, New Courthouse | Completed | Completed and Occupied | Completed | Completed | Completed | Completed | 27719000 | Completed
[9 empty] | Subtotal | 125619000
General Funded Capital Projects
a | b | c | d |  | e | f | g | h | i | j | k
Estimated Schedule
# | Initial Year Authorized | County | Project Name |  | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
1 |  | Sacramento | Court of Appeal, Third Appellate, Library and Courts | Working Drawings | In Design | n/a | 3/2010 | 4/2010 | 1/2012 | 66234000
2 | 07-08 | Los Angeles | New Long Beach Courthouse | Acquisition close to finish; currently in finishing SD, | In Acquisition, Development Firms to submit proposals in Fall 2009 | 10/2009 | 3/2010 | 6/2010 | 9/2012 | 296635000
[9 empty] | Subtotal | 362869000
SB 1732 Capital Projects
a | b | c | d |  | e | f | g | h | i | j | k
Estimated Schedule
# | Initial Year Authorized | County | Project Name |  | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
1 | 07-08 | Calaveras | New San Andreas Courthouse | Preliminary Plans | In Design | Completed | 11/2010 | 11/2010 | 5/2012 | 43579000
2 | 05-06 | Contra Costa | New Antioch Area Courthouse | Construction | In Construction | Completed | Completed | 4/2009 | 9/2010 | 64729000
3 | 06-07 | Fresno | BF Sisk Conversion | Construction | In Construction | Completed | Completed | 7/2008 | 10/2010 | 70898000
4 | 07-08 | Lassen | New Susanville Courthouse | Working Drawings | In Design | Completed | 5/2010 | 6/2010 | 9/2011 | 38937000
5 | 07-08 | Madera | New Madera Courthouse | Acquisition/Preliminary Plans | In Acquisition and design has been authorized | 12/2010 | 7/2011 | 7/2011 | 3/2013 | 97815000
6 | 06-07 | Mono | New Mammoth Lakes Courthouse | Working Drawings | In Design | Completed | 1/2010 | 1/2010 | 6/2011 | 21522000
7 | 06-07 | Plumas/Sierra | New Portola/Loyalton Courthouse | Construction | In Construction | Completed | Completed | 10/2008 | 11/2009 | 6496000
8 | 07-08 | Riverside | New Mid-County Courthouse | Preliminary Plans | In Design | Completed | 11/2010 | 11/2010 | 7/2012 | 63507000
9 | 07-08 | San Benito | New Hollister Courthouse | Preliminary Plans | In Design | Completed | 2/2011 | 2/2011 | 8/2012 | 36156000
10 | 07-08 | San Bernardino | New San Bernardino Courthouse | Preliminary Plans | In Design | Completed | 1/2011 | 1/2011 | 1/2013 | 341905000
11 | 07-08 | San Joaquin | New Stockton Courthouse | Preliminary Plans | In Design | Completed | 8/2011 | 8/2011 | 8/2013 | 261979000
12 | 07-08 | Tulare | New Porterville Courthouse | Preliminary Plans | In Design | Completed | 8/2011 | 8/2011 | 1/2013 | 91902000
[9 empty] | Subtotal | 1139425000
[9 empty] | Total of current capital projects: | 1502294000
Grand total of all capital projects:
| Notes: | [8 empty] | 1627913000
Fresno COA - DGS managed
Fresno Juvenile - County managed
These are current estimated project schedules and may change.
There are current estimated project costs and may change.
Internal notes:
Project estimates based on most recent authorized project costs for FY 09-10; confirmed with AO's capital project summaries
Schedules based on progress reports
Orange - Previously DGS and then AOC
Sac COA - schedule here per SS, and not reflected in Sept progress report

## SB 1732 ungrouped (hidden)
Completed Capital Projects
a | b | c | d | e | f | g | h | i | j
Estimated Schedule
# | County | Project Name | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
| Fresno | Court of Appeal, Fifth Appellate District | Completed and Occupied | Completed | Completed | Completed | Completed
| Merced | New Merced Downtown Courthouse | Completed and Occupied | Completed | Completed | Completed | Completed
| Fresno | New Fresno Area Juvenile Delinquency Courthouse | Completed and Occupied | n/a | Completed | Completed | Completed | 40319902
| Orange | Court of Appeal, Fourth Appellate District Division 3, New Courthouse | Completed and Occupied | Completed | Completed | Completed | Completed | 27719000
| Sacramento | Court of Appeal, Third Appellate, Library and Courts | In Design | n/a | 3/2010 | 4/2010 | 1/2012 | 66234000
| Los Angeles | New Long Beach Courthouse | In Acquisition, Development Firms to submit proposals in Fall 2009 | 10/2009 | 3/2010 | 5/2010 | 9/2012 | 296635000
| Calaveras | New San Andreas Courthouse | In Design | Completed | 11/2010 | 11/2010 | 5/2012 | 43579000
| Contra Costa | New Antioch Area Courthouse | In Construction | Completed | Completed | 4/2009 | 9/2010 | 64729000
| Fresno | BF Sisk Conversion | In Construction | Completed | Completed | 7/2008 | 10/2010 | 70898000
| Lassen | New Susanville Courthouse | In Design | Completed | 5/2010 | 6/2010 | 9/2011 | 38937000
| Madera | New Madera Courthouse | In Acquisition and design has been authorized | 12/2010 | 7/2011 | 7/2011 | 3/2013 | 97815000
| Mono | New Mammoth Lakes Courthouse | In Design | Completed | 12/2009 | 12/2009 | 6/2011 | 21522000
| Plumas/Sierra | New Portola/Loyalton Courthouse | In Construction | Completed | Completed | 10/2008 | 11/2009 | 6496000
| Riverside | New Mid-County Courthouse | In Design | Completed | 11/2010 | 11/2010 | 7/2012 | 63507000
| San Benito | New Hollister Courthouse | In Design | Completed | 2/2011 | 2/2011 | 8/2012 | 36156000
| San Bernardino | New San Bernardino Courthouse | In Design | Completed | 1/2011 | 1/2011 | 1/2013 | 341905000
| San Joaquin | New Stockton Courthouse | In Design | Completed | 8/2011 | 8/2011 | 8/2013 | 261279000
| Tulare | New Porterville Courthouse | In Design | Completed | 8/2011 | 8/2011 | 12/2012 | 91902000
Subtotal
| Completed or other funding | [5 empty] | Grand total
Merced - COMPLETED - County managed, AOC contributed funds
Fresno COA - COMPLETED - DGS, AOC contributed funds
Fresno Juvenile - COMPLETED - County manged, AOC contributed funds
Orange COA - COMPLETED
Sacramento COA- OTHER FUNDING - DGS
Long Beach - OTHER FUNDING
Notes:
Estimated schedule - These dates are estimated and are subject to change.
Total project estimated cost - These costs are estimated and are subject to change.

## SB 1407 (15)
SB 1407 Capital Projects - Initial Group Authorized (15 projects)
a | b | b | c | d | e | f | g | h | i | j
Estimated Schedule1
# | Group | Initial Year Authorized | County | Project Name | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost2
1 | SB 1407-Group 1 | 09-10 | Butte | New North Butte County Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Spring 2013 | Spring 2013 | Fall 2014 | 83367000
2 | SB 1407-Group 1 | 09-10 | Los Angeles | New Southeast Los Angeles Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Summer 2013 | Summer 2013 | Winter 2015 | 129027000
3 | SB 1407-Group 1 | 09-10 | Tehama | New Red Bluff Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Summer 2013 | Summer 2013 | Winter 2015 | 78131000
4 | SB 1407-Group 1 | 09-10 | Yolo | New Woodland Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Summer 2013 | Fall 2013 | Spring 2015 | 172940000
5 | SB 1407-Group 1 | 09-10 | Imperial | New El Centro Family Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Winter 2013 | Winter 2013 | Summer 2014 | 77288000
6 | SB 1407-Group 1 | 09-10 | Lake | New Lakeport Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Spring 2013 | Spring 2013 | Winter 2015 | 71744000
7 | SB 1407-Group 1 | 09-10 | Monterey | New South County Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Spring 2013 | Spring 2013 | Winter 2015 | 65220000
8 | SB 1407-Group 1 | 09-10 | Riverside | New Indio Juvenile and Family Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Spring 2013 | Spring 2013 | Fall 2014 | 84415000
9 | SB 1407-Group 1 | 09-10 | Sacramento | New Sacramento Criminal Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Winter 2013 | Winter 2013 | Spring 2015 | 509230000
10 | SB 1407-Group 1 | 09-10 | Shasta | New Redding Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Winter 2013 | Winter 2013 | Winter 2015 | 211779000
11 | SB 1407-Group 1 | 09-10 | Sonoma | New Santa Rosa Criminal Courthouse | Acquisition/ Design Team Selected | Summer 2011 | Fall 2012 | Fall 2012 | Fall 2014 | 240125000
12 | SB 1407-Group 1 | 09-10 | Sutter | New Yuba City Courthouse | Acquisition/ Design Team Selected | Summer 2010 | Spring 2012 | Spring 2012 | Fall 2013 | 100626000
13 | SB 1407-Group 1 | 09-10 | Solano | Renovation to Fairfield Old Solano Courthouse | Acquisition/ Design Team Selected | Winter 2010 | Summer 2011 | Summer 2011 | Summer 2012 | 26893000
14 | SB 1407-Group 1 | 09-10 | Alameda | New East County Courthouse (Criminal) | Acquisition/ Design Team Selected | Not Applicable | Summer 2011 | Summer 2011 | Summer 2013 | $ 130,010,000
15 | SB 1407-Group 1 | 09-10 | Santa Clara | New Family Justice Center (San Jose Family Resources Courthouse) | Acquisition/ Design Team Selected | Fall 2010 | Summer 2011 | Summer 2011 | Summer 2013 | $ 184,080,000
[9 empty] | Total (4): | 2164875000
Notes:
1. Current estimated project schedules and may change.
2. Current total estimated project costs and may change.
Internal Notes:
Project costs based on FY 09-10 most recently authorized legislation, not 10-11 costs.
Project schedules based on October 2009 progress reports.
OCTOBER VERSION - Schedules based on excel bar chart provided by Denise 10/16/09: \\jcc\aocdata\aocshared\OCCM\JLBC - SB 1407\Group 2A 091020\SB1407 Funded Projects Projected Schedules.xlsx

## SB 1407 (remain 26)
SB 1407 Capital Projects - Pending Authorization (26 projects)
a | b | b | c | d | e | f | g | h | i | j
Estimated Schedule2
# | Group | Initial Year Authorized | County | Project Name | Project Status: Authorized Continuous Appropriation (estimated PWB approval date)1 | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost3
1 | SB 1407-Group 2A | 09-10 | Inyo | New Independence Courthouse | Completed | Fall 2011 | Winter 2013 | Spring 2013 | Spring 2014 | 32286000
2 | SB 1407-Group 2A | 09-10 | Kern | New Delano Courthouse | Completed | Fall 2011 | Spring 2013 | Spring 2013 | Fall 2014 | 41924000
3 | SB 1407-Group 2A | 09-10 | Los Angeles | New Santa Clarita Courthouse | Completed | Fall 2011 | Spring 2013 | Spring 2013 | Fall 2014 | 58131000
4 | SB 1407-Group 2A | 09-10 | Merced | New Los Banos Courthouse | Completed | Fall 2011 | Winter 2013 | Spring 2013 | Winter 2014 | 32597000
5 | SB 1407-Group 2A | 09-10 | San Diego | New Central San Diego Courthouse | Completed | Spring 2011 | Summer 2013 | Summer 2013 | Winter 2016 | 633134000
6 | SB 1407-Group 2A | 09-10 | Tuolumne | New Sonora Courthouse | Completed | Fall 2011 | Spring 2013 | Spring 2013 | Fall 2014 | 70076000
7 | SB 1407-Group 2B | 09-10 | El Dorado | New Placerville Courthouse | 12/2009 | Fall 2011 | Summer 2013 | Summer 2013 | Winter 2014 | 89426000
8 | SB 1407-Group 2B | 09-10 | Kings | New Hanford Courthouse | 12/2009 | Fall 2011 | Summer 2013 | Fall 2013 | Summer 2015 | 142449000
9 | SB 1407-Group 2B | 09-10 | Los Angeles | New Glendale Courthouse | 12/2009 | Fall 2011 | Fall 2013 | Fall 2013 | Spring 2015 | 123948000
10 | SB 1407-Group 2B | 09-10 | Mendocino | New Ukiah Courthouse | 12/2009 | Fall 2011 | Fall 2013 | Fall 2013 | Spring 2015 | 119914000
11 | SB 1407-Group 2B | 09-10 | Siskiyou | New Yreka Courthouse | 12/2009 | Fall 2011 | Summer 2013 | Fall 2013 | Winter 2014 | 96501000
12 | SB 1407-Group 2C | 09-10 | Fresno | Renovate Fresno County Courthouse | 2/2010 | not applicable4 | Winter 2012 | Winter 2012 | Winter 2014 | 107365000
13 | SB 1407-Group 2C | 09-10 | Glenn | Renovation and Addition to Willows Historic Courthouse | 2/2010 | not applicable4 | Winter 2012 | Winter 2012 | Winter 2014 | 32686000
14 | SB 1407-Group 2C | 09-10 | Los Angeles | Renovate Lancaster Juvenile Courthouse | 2/2010 | not applicable4 | Spring 2011 | Spring 2011 | Summer 2012 | 8431000
15 | SB 1407-Group 2C | 09-10 | Santa Barbara | Renovation and Addition to Figueroa Courthouse | 2/2010 | Fall 2011 | Fall 2013 | Winter 2013 | Fall 2015 | 126624000
16 | SB 1407-Group 2C | 09-10 | Stanislaus | New Modesto Courthouse | 2/2010 | Fall 2011 | Fall 2013 | Winter 2013 | Fall 2015 | 113897000
17 | SB 1407-Group 3A | 09-10 | Alpine | New Markleeville Courthouse | 3/2010 | Winter 2012 | Spring 2013 | Summer 2013 | Fall 2014 | 13515000
18 | SB 1407-Group 3A | 09-10 | Sierra | New Downieville Courthouse | 3/2010 | Winter 2012 | Spring 2013 | Summer 2013 | Fall 2014 | 13515000
19 | SB 1407-Group 3B | 09-10 | Kern | New Mojave Courthouse | 4/2010 | Spring 2012 | Fall 2013 | Fall 2013 | Spring 2015 | 25140000
20 | SB 1407-Group 3B | 09-10 | Los Angeles | New Los Angeles Mental Health Courthouse | 4/2010 | Spring 2012 | Fall 2013 | Fall 2013 | Spring 2015 | 40545000
21 | SB 1407-Group 3B | 09-10 | Nevada | New Nevada City Courthouse | 4/2010 | Winter 2012 | Summer 2013 | Summer 2013 | Fall 2014 | 81091000
22 | SB 1407-Group 3B | 09-10 | Placer | New Tahoe Area Courthouse | 4/2010 | Winter 2012 | Summer 2013 | Summer 2013 | Fall 2014 | 12570000
23 | SB 1407-Group 3B | 09-10 | Plumas | New Quincy Courthouse | 4/2010 | Winter 2012 | Summer 2013 | Summer 2013 | Fall 2014 | 25140000
24 | SB 1407-Group 3C | 09-10 | Los Angeles | New Eastlake Juvenile Courthouse | 5/2010 | Spring 2012 | Fall 2013 | Fall 2013 | Summer 2015 | 67576000
25 | SB 1407-Group 3C | 09-10 | Riverside | Addition to Hemet Courthouse | 5/2010 | not applicable8 | Summer 2011 | Fall 2011 | Winter 2012 | 51224000
26 | SB 1407-Group 3C | 09-10 | San Joaquin | Renovate Juvenile Justice Center | 5/2010 | not applicable8 | Fall 2011 | Fall 2011 | Winter 2012 | 6252000
[9 empty] | Total (5): | 2165957000
[9 empty] | Total of all SB 1407 capital projects (subtotal 4+5): | 4330832000
[9 empty] | Total of current and active capital projects | 5766892000
Notes:
1. Estimated Public Works Board approval date and may change.
2. Current estimated project schedules and may change.
3. Current total estimated project costs and may change.
4. Acquisition not required on renovation projects.
Notes:

## SB 1407 (15) Old (hidden)
a | b | b | c | d |  | e | f | g | h | i | j
Estimated Schedule
# | Group | Initial Year Authorized | County | Project Name | Project Status | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost1 | Number of jobs created
1 | SB 1407-Group 1 | 08-09 | Butte | New North Butte County Courthouse | Acquisition | 6/2011 | 3/2013 | 4/2013 | 11/2014 | 83367000 | 2029
2 | SB 1407-Group 1 | 08-09 | Los Angeles | New Southeast Los Angeles Courthouse | Acquisition | 5/2011 | 6/2013 | 7/2013 | 2/2015 | 129027000 | 3139
3 | SB 1407-Group 1 | 08-09 | Tehama | New Red Bluff Courthouse | Acquisition | 9/2011 | 6/2013 | 7/2013 | 5/2015 | 78131000 | 1900
4 | SB 1407-Group 1 | 08-09 | Yolo | New Woodland Courthouse | Acquisition | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 172940000 | 4207
5 | SB 1407-Group 1 | 09-10 | Imperial | New El Centro Family Courthouse | Acquisition | 5/2011 | 12/2012 | 12/2012 | 12/2014 | 77288000 | 1881
6 | SB 1407-Group 1 | 09-10 | Lake | New Lakeport Courthouse | Acquisition | 9/2011 | 4/2013 | 5/2013 | 1/2015 | 71744000 | 1745
7 | SB 1407-Group 1 | 09-10 | Monterey | New South County Courthouse | Acquisition | 5/2011 | 4/2013 | 5/2013 | 1/2015 | 65220000 | 1587
8 | SB 1407-Group 1 | 09-10 | Riverside | New Indio Juvenile and Family Courthouse | Acquisition | 5/2011 | 5/2013 | 5/2013 | 10/2014 | 84415000 | 2054
9 | SB 1407-Group 1 | 09-10 | Sacramento | New Sacramento Criminal Courthouse | Acquisition | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 509230000 | 12391
10 | SB 1407-Group 1 | 09-10 | Shasta | New Redding Courthouse | Acquisition | 5/2011 | 5/2012 | 6/2012 | 10/2014 | 211779000 | 5154
11 | SB 1407-Group 1 | 09-10 | Sonoma | New Santa Rosa Criminal Courthouse | Acquisition | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 240125000 | 5843
12 | SB 1407-Group 1 | 09-10 | Sutter | New Yuba City Courthouse | Acquisition | 5/2011 | 4/2013 | 5/2013 | 7/2014 | 100626000 | 2448
13 | SB 1407-Group 1 | 09-10 | Solano | Renovation to Fairfield Old Solano Courthouse | Acquisition | 7/2009 | 11/2010 | 11/2010 | 9/2012 | 26893000 | 655
14 | SB 1407-Group 1 | 09-10 | Alameda | New East County Courthouse (Criminal) | Acquisition | 7/2009 | 5/2010 | 5/2010 | 3/2012 | 130010000 | 3163
15 | SB 1407-Group 1 | 09-10 | Santa Clara | New Family Justice Center (San Jose Family Resources Courthouse) | Acquisition | 7/2009 | 8/2011 | 8/2011 | 6/2013 | 184080000 | 4480
[9 empty] | Total | 2164875000 | 52676
Notes:
These are current estimated project schedules and may change.
There are current estimated project costs and may change.
Authorized in legislation FY 08-09; funding provided in FY 09-10
Job creation footnote: Fuller, Stephen S., “The Contribution of Office, Industrial, and Retail Development and Construction on California’s Economy,” from a report prepared for the National Association of Industrial and Office Properties Research Foundation, The Contribution of Office, Industrial and Retail Development on the U.S. Economy (January 2007).
14.67 million is creating 308,938 jobs
Alameda - $50,000,000 AOC contribution, County/State funded project.
Santa Clara - $44,000,000 AOC contribution
Internal notes:
These projects have been authorized and are based on the 9/15/09 costs.
Schedules based on MS project provided by Denise which includes continuous appropriation schedule (8/29/09)

## SB 1407 (remain 26) (Old) (hidden)
a | b | b | c | d | e | f | g | h | i | j | k
Estimated Schedule
# | Group | Initial Year Authorized | County | Project Name | Project Status Authorized Continuous Appropriation (estimated PWB approval date) | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Estimated Number of Jobs Created
1 | SB 1407-Group 3A |  | Alpine | New Markleeville Courthouse | 3/2010 | 1/2012 | 6/2013 | 6/2013 | 4/2015 | 83367000 | 329
2 | SB 1407-Group 2B |  | El Dorado | New Placerville Courthouse | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 129027000 | 1973
3 | SB 1407-Group 2C |  | Fresno | Renovate Fresno County Courthouse | 2/2010 | 1/2010 | 6/2011 | 6/2011 | 4/2013 | 78131000 | 2613
4 | SB 1407-Group 2C |  | Glenn | Renovation and Addition to Willows Historic Courthouse | 2/2010 | 2/2010 | 7/2011 | 7/2011 | 5/2013 | 172940000 | 796
5 | SB 1407-Group 2A |  | Inyo | New Independence Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 77288000 | 786
6 | SB 1407-Group 2A |  | Kern | New Delano Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 71744000 | 1020
7 | SB 1407-Group 3B |  | Kern | New Mojave Courthouse | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 65220000 | 611
8 | SB 1407-Group 2B |  | Kings | New Hanford Courthouse | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 84415000 | 2959
9 | SB 1407-Group 2A |  | Los Angeles | New Santa Clarita Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 509230000 | 1414
10 | SB 1407-Group 2B |  | Los Angeles | New Glendale Courthouse | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 211779000 | 3117
11 | SB 1407-Group 2C |  | Los Angeles | Renovate Lancaster Juvenile Courthouse | 2/2010 | 1/2010 | 6/2011 | 6/2011 | 4/2013 | 240125000 | 204
12 | SB 1407-Group 3B |  | Los Angeles | New Los Angeles Mental Health Courthouse | 4/2010 | 3/2012 | 8/2013 | 8/2013 | 6/2015 | 100626000 | 986
13 | SB 1407-Group 3C |  | Los Angeles | New Eastlake Juvenile Courthouse | 5/2010 | 2/2012 | 6/2013 | 6/2013 | 4/2015 | 26893000 | 1645
14 | SB 1407-Group 2B |  | Mendocino | New Ukiah Courthouse | 12/2009 | 9/2011 | 11/2012 | 11/2012 | 9/2014 | 130010000 | 2959
15 | SB 1407-Group 2A |  | Merced | New Los Banos Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 184080000 | 793
16 | SB 1407-Group 3B |  | Nevada | New Nevada City Courthouse | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 2164875000 | 1973
17 | SB 1407-Group 3B |  | Placer | New Tahoe Area Courthouse | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 12570000 | 307
18 | SB 1407-Group 3B |  | Plumas | New Quincy Courthouse | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 25140000 | 611
19 | SB 1407-Group 3C |  | Riverside | Addition to Hemet Courthouse | 5/2010 | 7/2010 | 11/2011 | 11/2011 | 9/2013 | 51224000 | 1246
20 | SB 1407-Group 2A |  | San Diego | New Central San Diego Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 660134000 | 16063
21 | SB 1407-Group 3C |  | San Joaquin | Renovate Juvenile Justice Center | 5/2010 | 6/2010 | 11/2011 | 11/2011 | 9/2013 | 6252000 | 153
22 | SB 1407-Group 2C |  | Santa Barbara | Renovation and Addition to Figueroa Courthouse | 2/2010 | 3/2010 | 7/2011 | 7/2011 | 7/2013 | 126624000 | 3081
23 | SB 1407-Group 3A |  | Sierra | New Downieville Courthouse | 3/2010 | 1/2012 | 6/2013 | 6/2013 | 4/2015 | 13515000 | 329
24 | SB 1407-Group 2B |  | Siskiyou | New Yreka Courthouse | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 76540000 | 1862
25 | SB 1407-Group 2C |  | Stanislaus | New Modesto Courthouse | 2/2010 | 12/2011 | 5/2013 | 5/2013 | 3/2015 | 113897000 | 2772
26 | SB 1407-Group 2A |  | Tuolumne | New Sonora Courthouse | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 70076000 | 1720
[9 empty] | Total | 5485722000 | 52322
Notes:
These are estimated project schedules and are subject to change.
There are estimated project costs and are subject to change.
Job creation footnote: Fuller, Stephen S., “The Contribution of Office, Industrial, and Retail Development and Construction on California’s Economy,” from a report prepared for the National Association of Industrial and Office Properties Research Foundation, The Contribution of Office, Industrial and Retail Development on the U.S. Economy (January 2007).
Internal notes:
Approved by DOF and with JLBC (6) and used JLBC projects costs- Inyo, Kern, LA Santa Clarita, Merced, San Diego and Tuolumne
Draft to DOF (5) used original project budget- El Dorado, Kings, LA Glendale, Mendocino, Siskiyou
(15) remaining projects used original project budget
Schedules based on MS project provided by Denise which includes continuous appropriation schedule (8/29/09)
Notes:

## SB 1407 old (hidden)
SB 1407 - Group One
a | b | b | c | d | e | f | g | h | i | j | k
Estimated Schedule
# | Group | County | Project Name | Authorized in FY 09-10 Budget Act | Authorized Continuous Appropriation (estimated PWB approval date) | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost1 | Number of jobs created
1 | SB 1407-Group 1 | Butte | New North Butte County Courthouse | 7/2009 |  | 6/2011 | 3/2013 | 4/2013 | 11/2014 | 83367000 | 2064
2 | SB 1407-Group 1 | Los Angeles | New Southeast Los Angeles Courthouse | 7/2009 |  | 5/2011 | 6/2013 | 7/2013 | 2/2015 | 129027000 | 3193
3 | SB 1407-Group 1 | Tehama | New Red Bluff Courthouse | 7/2009 |  | 9/2011 | 6/2013 | 7/2013 | 5/2015 | 78131000 | 1933
4 | SB 1407-Group 1 | Yolo | New Woodland Courthouse | 7/2009 |  | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 172940000 | 4280
5 | SB 1407-Group 1 | Imperial | New El Centro Family Courthouse | 7/2009 |  | 5/2011 | 12/2012 | 12/2012 | 12/2014 | 77288000 | 1913
6 | SB 1407-Group 1 | Lake | New Lakeport Courthouse | 7/2009 |  | 9/2011 | 4/2013 | 5/2013 | 1/2015 | 71744000 | 1775
7 | SB 1407-Group 1 | Monterey | New South County Courthouse | 7/2009 |  | 5/2011 | 4/2013 | 5/2013 | 1/2015 | 65220000 | 1614
8 | SB 1407-Group 1 | Riverside | New Indio Juvenile and Family Courthouse | 7/2009 |  | 5/2011 | 5/2013 | 5/2013 | 10/2014 | 84415000 | 2089
9 | SB 1407-Group 1 | Sacramento | New Sacramento Criminal Courthouse | 7/2009 |  | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 509230000 | 12604
10 | SB 1407-Group 1 | Shasta | New Redding Courthouse | 7/2009 |  | 5/2011 | 5/2012 | 6/2012 | 10/2014 | 211779000 | 5243
11 | SB 1407-Group 1 | Sonoma | New Santa Rosa Criminal Courthouse | 7/2009 |  | 5/2011 | 9/2012 | 9/2012 | 7/2014 | 240125000 | 5943
12 | SB 1407-Group 1 | Sutter | New Yuba City Courthouse | 7/2009 |  | 5/2011 | 4/2013 | 5/2013 | 7/2014 | 100626000 | 2490
13 | SB 1407-Group 1 | Solano | Renovation to Fairfield Old Solano Courthouse | 7/2009 |  | 7/2009 | 11/2010 | 11/2010 | 9/2012 | 25418000 | 629
14 | SB 1407-Group 1 | Alameda | New East County Courthouse (Criminal) | 7/2009 |  | 7/2009 | 5/2010 | 5/2010 | 3/2012 | 50000000 | 1238
15 | SB 1407-Group 1 | Santa Clara | New Family Justice Center (San Jose Family Resources Courthouse) | 7/2009 |  | 7/2009 | 8/2011 | 8/2011 | 6/2013 | 44000000 | 1089
[9 empty] | Group One Total | 1943310000
SB 1407 - Group Two
a | b | b | c | d | e | f | g | h | i | j | k
Estimated Schedule
# | Group | County | Project Name | Authorized in FY 09-10 Budget Act | Authorized Continuous Appropriation (estimated PWB approval date) | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
16 | SB 1407-Group 2A | Inyo | New Independence Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 32286000 | 800
17 | SB 1407-Group 2A | Kern | New Delano Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 41924000 | 1037
18 | SB 1407-Group 2A | Los Angeles | New Santa Clarita Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 58131000 | 1438
19 | SB 1407-Group 2A | Merced | New Los Banos Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 32597000 | 807
20 | SB 1407-Group 2A | San Diego | New Central San Diego Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 660134000 | 16339
21 | SB 1407-Group 2A | Tuolumne | New Sonora Courthouse |  | 11/2009 | 8/2011 | 1/2013 | 1/2013 | 11/2014 | 70076000 | 1735
22 | SB 1407-Group 2B | El Dorado | New Placerville Courthouse |  | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 101297000 | 2507
23 | SB 1407-Group 2B | Kings | New Hanford Courthouse |  | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 142449000 | 3525
24 | SB 1407-Group 2B | Los Angeles | New Glendale Courthouse |  | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 123948000 | 3067
25 | SB 1407-Group 2B | Mendocino | New Ukiah Courthouse |  | 12/2009 | 9/2011 | 11/2012 | 11/2012 | 9/2014 | 119914000 | 2968
26 | SB 1407-Group 2B | Siskiyou | New Yreka Courthouse |  | 12/2009 | 9/2011 | 2/2013 | 2/2013 | 12/2014 | 96501000 | 2389
27 | SB 1407-Group 2C | Fresno | Renovate Fresno County Courthouse |  | 2/2010 | 1/2010 | 6/2011 | 6/2011 | 4/2013 | 107365000 | 2658
28 | SB 1407-Group 2C | Glenn | Renovation and Addition to Willows Historic Courthouse |  | 2/2010 | 2/2010 | 7/2011 | 7/2011 | 5/2013 | 32686000 | 809
29 | SB 1407-Group 2C | Los Angeles | Renovate Lancaster Juvenile Courthouse |  | 2/2010 | 1/2010 | 6/2011 | 6/2011 | 4/2013 | 8431000 | 208
30 | SB 1407-Group 2C | Santa Barbara | Renovation and Addition to Figueroa Courthouse |  | 2/2010 | 3/2010 | 7/2011 | 7/2011 | 7/2013 | 141350109 | 3500
31 | SB 1407-Group 2C | Stanislaus | New Modesto Courthouse |  | 2/2010 | 12/2011 | 5/2013 | 5/2013 | 3/2015 | 117808869 | 2916
[9 empty] | Group Two Total | 1886897978
SB 1407 - Group Three
a | b | b | c | d | e | f | g | h | i | j | k
Estimated Schedule
# | Group | County | Project Name | Authorized in FY 09-10 Budget Act | Authorized Continuous Appropriation (estimated PWB approval date) | Acquisition Finish Date | Design Finish Date | Construction Start date | Construction Finish Date | Total Estimated Project Cost | Number of jobs created
32 | SB 1407-Group 3A | Alpine | New Markleeville Courthouse |  | 3/2010 | 1/2012 | 6/2013 | 6/2013 | 4/2015 | 16300000 | 403
33 | SB 1407-Group 3A | Sierra | New Downieville Courthouse |  | 3/2010 | 1/2012 | 6/2013 | 6/2013 | 4/2015 | 16300000 | 403
34 | SB 1407-Group 3B | Kern | New Mojave Courthouse |  | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 44178326 | 1094
35 | SB 1407-Group 3B | Los Angeles | New Los Angeles Mental Health Courthouse |  | 4/2010 | 3/2012 | 8/2013 | 8/2013 | 6/2015 | 44178326 | 1094
36 | SB 1407-Group 3B | Nevada | New Nevada City Courthouse |  | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 88356652 | 2188
37 | SB 1407-Group 3B | Placer | New Tahoe Area Courthouse |  | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 16300000 | 403
38 | SB 1407-Group 3B | Plumas | New Quincy Courthouse |  | 4/2010 | 2/2012 | 7/2013 | 7/2013 | 5/2015 | 32600000 | 807
39 | SB 1407-Group 3C | Los Angeles | New Eastlake Juvenile Courthouse |  | 5/2010 | 2/2012 | 6/2013 | 6/2013 | 4/2015 | 73630543 | 1822
40 | SB 1407-Group 3C | Riverside | Addition to Hemet Courthouse |  | 5/2010 | 7/2010 | 11/2011 | 11/2011 | 9/2013 | 73630543 | 1822
41 | SB 1407-Group 3C | San Joaquin | Renovate Juvenile Justice Center |  | 5/2010 | 6/2010 | 11/2011 | 11/2011 | 9/2013 | 6252000 | 156
[9 empty] | Group Three Total | 411726390
[7 empty] | Total of Estimated Project Budgets for 41 Projects |  |  | 4241934368
[8 empty] | Program Contingency of 10% |  | 424193436.8
| Notes: | Note: |  |  |  |  | Total SB 1407 Capital Program Budget |  |  | 4666127804.8
1. Revised SB 1407 Budget: Group 1: Latest COBCPs to June 2009; Groups 2 and 3: Project costs in bold above based on August 6, 2009 draft COBCP submission, and renovations to be held at original budget, Average Cost per Courtroom of $14.9 million based on August 6, 2009 submission (excluding San Diego) applied to other projects, except as follows: Group 3 - 1 and 2 courtroom "snow-country" projects are based on $16.3 million per courtroom (Merced 3PE). Glenn budget was held at original budget, which is close to a 2 courtroom replacement cost and should therefore be conservative. Santa Barbara is based on original budget plus 1 courtroom at $14.99 million due to adding one courtroom to program. Riverside-Hemet budgeted as if it is a new building because expansion feasibility is a question.