Standard Agreement

JUDICIAL COUNCIL OF CALIFORNIA, ADMINISTRATIVE OFFICE OF THE COURTS

|  |  | AGREEMENT NUMBER |
| --- | --- | --- |
|  |  | @ct |
|  |  | FEDERAL EMPLOYER ID NUMBER |
| THIS AGREEMENT is made and entered into this __ day of ____ (“Effective Date”), in the State of California, by and between the parties identified below. |  |  |
| In this agreement (the “Agreement”), the term “Contractor” refers to @contractor and the term “AOC” refers to the Judicial Council of California, Administrative Office of the Courts. |  |  |
| Incorporated into this Agreement herewith, and attached hereto, are the following documents (“Contract Documents”): (1) Exhibit A, Standard Provisions; (2) Exhibit B, Special Provisions; (3) Exhibit C, Work Order Authorization Process and Payment Provisions; (4) Exhibit D, Statement of Work, (5) Exhibit E Services Request Form, (6) Exhibit F, Work Order Authorization Form and (7) Exhibit G, Acceptance and Signoff Form. In the event of a conflict between the Contract Documents, the following descending order of precedence shall govern: Exhibit A, Exhibit B, Exhibit C, and Exhibit D. Any Amendments, starting with the most recent, shall take precedence over the existing Agreement. As set forth in this Agreement, and as specified in Work Orders authorized under this Agreement, the Contractor agrees to provide the Work as specified. The term of this Agreement begins on the Effective Date and expires on _____, unless otherwise extended by amendment of this Agreement. |  |  |

| AOC’S SIGNATURE | CONTRACTOR’S SIGNATURE |
| --- | --- |
| Judicial Council of California, Administrative Office of the Courts | CONTRACTOR’S NAME (if Contractor is not an individual person, state whether Contractor is a corporation, partnership, etc.) 1015771tr |
| BY (Authorized Signature)  | BY (Authorized Signature)  |
| PRINTED NAME AND TITLE OF PERSON SIGNING Grant Walker Senior Manager, Business Services | PRINTED NAME AND TITLE OF PERSON SIGNING |
| ADDRESS 455 Golden Gate Avenue San Francisco, CA 94102 | ADDRESS |

Administrative Office of the Courts Use Only

| Fund Title | Program/ Category | Item |  | Chapter | Statute | Fiscal Year | Object of Expenditure |  |  | Amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Amount Encumbered by this Document: |  |  | Prior Amount Encumbered for this Contract: |  |  |  |  | Total Amount Encumbered to Date: |  |  |
| $0.00 |  |  | $0.00 |  |  |  |  | $0.00 |  |  |
| I hereby certify upon my own personal knowledge that budgeted funds are available for the period of the expenditure stated above. |  |  |  |  |  |  |  |  |  |  |
| SIGNATURE OF ACCOUNTING OFFICER  |  |  |  |  |  |  |  |  | DATE |  |

EXHIBIT A

STANDARD PROVISIONS

- Indemnification

Contractor agrees, to the fullest extent permitted by law, to indemnify, defend (with counsel satisfactory to the AOC), and hold harmless (collectively, “Indemnify”) the State, the Judicial Council of California, the Administrative Office of the Courts, the State’s trial courts, appellate courts, justices, judges, subordinate judicial officers, court executive officers, court administrators, and any and all of their officers, agents, contractors, representatives, volunteers and employees (individually, an “Indemnified Party”) from any and all claims, lawsuits, losses, costs (including attorney fees and costs), liabilities, and damages  arising from, related to or in connection with, in whole or in part, any of the following:

(a) Contractor or any of its employees’ or Subcontractor’s negligent acts, omissions, or intentional misconduct;

(b) Contractor’s breach of its obligations under this Agreement;

(c) Contractor or any of its employees’ or Subcontractor’s violation of any applicable law, rule, or regulation; and/or

(d) Any claim or lawsuit by any third party, who may be injured or damaged by the negligent actions of theContractor or any of its Subcontractors, or employees when such claim arises from, is related to, or is in connection with the Contractor’s performance under this Agreement.

This article does not require the Contractor to Indemnify an Indemnified Party for such portion of any loss, cost, liability, or damage that arises  from the negligence or intentional misconduct of the Indemnified Party, or as a result of specific directions provided to the Contractor by an Indemnified party, or as a result of actions by the Contractor performed in the completion of the Scope of Services.

- Relationship of Parties

##### Contractor and its employees and Subcontractors, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State.

- Termination for Cause

##### The State may terminate this Agreement or any individual Work Order, and be relieved of the payment of any consideration to Contractor for any Work not yet completed and accepted if Contractor fails to perform as specified in this Agreement at the time and in the manner provided.  If the Agreement or a Work Order is terminated, the State may proceed with the Work in any manner it deems proper.  The cost to the State to perform the Work shall be deducted from any sum due Contractor under this Agreement or any other agreement, and the balance, if any, shall be paid to Contractor upon demand.

- No Assignment

##### Without the written consent of the State, Contractor shall not assign this Agreement in whole or in part.

- Time of Essence

##### Time is of the essence in this Agreement.

- Validity of Alterations

##### Alteration or variation of the terms of this Agreement shall not be valid unless made in writing and signed by the parties, and an oral understanding or agreement that is not incorporated shall not be binding on any of the parties.

- Consideration

The consideration to be paid to Contractor under this Agreement shall in no event exceed the Contract Amount.  Contractor shall be paid in accordance with the Payment Provisions set forth in Exhibit "C" of this Agreement.  The State's payments to Contractor pursuant to this section shall constitute full compensation for all of Contractor's time, materials, costs and expenses incurred in the performance of this Agreement.

END OF EXHIBIT

EXHIBIT B

SPECIAL PROVISIONS

- Definitions

##### Terms defined below and elsewhere throughout the Contract Documents shall apply to the Agreement as defined. Additional terms may be defined in authorized Work Orders, however, the definition of a term defined in a Work Order shall apply only within the Work Order in which it is defined.

  - “Acceptance” means the written acceptance issued to Contractor by the State’s Project Manager after Contractor has completed a Deliverable, in compliance with this Agreement, including without limitation,  D, the Statement of Work and the applicable Work Order.

  - "Administrative Director" refers to that individual or authorized designee, empowered by the State to make final and binding executive decisions on behalf of the State.

  - “Amendment” means a written document issued by the State and signed by Contractor which alters the Agreement or a Work Order authorized under the Agreement and which identifies the following: (1) a change in the Work; (2) a change in the “Total Amount Encumbered to Date” under a Work Order; or (3) an adjustment to the Agreement terms.

  - “Business Day” means days of the week excluding Saturday and Sunday, as well as Contractor’s pre-established and published holidays applicable to its employees.

  - “Confidential Information” means trade secrets, financial, statistical, personnel, technical, and other Data and information relating to the State’s business or the business of its constituents.  Confidential Information does not include (i) information that is already known by the receiving party, free of obligation of confidentiality to the disclosing party; (ii) information that becomes generally available to the public, other than as a result of disclosure by the receiving party in breach of this Agreement; (iii) information that is independently developed by the receiving party without reference to the Confidential Information; and (iv) information that the receiving party rightfully obtains from a Third Party free of the obligation of confidentiality to the disclosing party.

  - The “Agreement” constitutes the entire integrated agreement between the State and Contractor, and includes the Contract Documents incorporated by reference into a fully executed State Standard Agreement form.  The term “Contract” may be used interchangeably with the term “Agreement.”

  - “Contract Amount” means the total amount encumbered under this Agreement for payment by the State to Contractor for performance of all Work Orders and reimbursement of all expenses, in accordance with the Contract Documents.

  - The “Contractor” means the individual, association, partnership, firm, company, consultant, corporation, affiliates, or combination thereof, including joint ventures, contracting with the State to do the Contract Work.  Contractor is one of the parties to this Agreement.

  - “Court(s)” or “Trial Court(s)” means one or more of the fifty-eight (58) superior courts in the California state trial court system.

  - “Data” means all types of raw data, articles, papers, charts, records, reports, studies, research, memoranda, computation sheets, questionnaires, surveys, and other documentation.

  - “Day” means calendar day.

  - “Deliverable(s)” means and includes any tangible item provided or to be provided under this Agreement, including written reports. Services may be performed in pursuit of providing Deliverable(s), however, a Deliverable may not consist solely of the performance of Services.

  - “Deliverable Basis” means that the Services provided under a Work Order shall result in the provision of a Deliverable or Deliverables.

  - “Expenses” means and includes both Travel and Living Expenses and Reimbursable Expenses.

  - “Firm Fixed Price” means a single fixed amount or amounts designated as payment for a Deliverable or Deliverables in a Work Order.

  - “Firm Fixed Price Basis” means that the Contractor shall receive, as full and complete compensation for the provision of Deliverable(s), Firm Fixed Price(s),which shall constitute complete compensation for all costs, expenses, and efforts incurred by Contractor in provision of the Deliverable(s).

  - “Force Majeure” means a delay which impacts the timely performance of Work which neither Contractor nor the State are liable because such delay or failure to perform was unforeseeable and beyond the control of the party. Acts of Force Majeure include, but are not limited to:

Acts of God or the public enemy;

Acts or omissions of any government entity;

Fire or other casualty for which a party is not responsible;

Quarantine or epidemic;

Strike or defensive lockout; and,

Unusually severe weather conditions.

  - “Hourly Basis” means that Contractor shall be paid at an hourly rate for each such hour of authorized Work actually performed.

  - “Key Personnel” refers to Contractor’s personnel or personnel of Subontractors that are named in Work Orders, whom the State has approved to perform specific Work.  Qualifications of Key Personnel are provided in any resumes set forth in or attached to Work Orders.  Work and roles of Key Personnel are as set forth in this Agreement and in Work Orders.

  - “Material” means all types of tangible personal property, including but not limited to reports, goods, supplies, equipment, commodities, and information and telecommunication technology.

  - “Notice” means a written document as required by this Agreement and given by:

Depositing in the U. S. Mail (or approved commercial express carrier) prepaid to the address of the appropriate authorized representative of the other party, which shall be effective upon date of receipt; or hand-delivered to the other party’s authorized representative, which shall be effective on the date of service.

  - “Project” refers to all activity relative to an individual Work Order executed under this Agreement, including the Work of Contractor and its Subcontractors and the responsibilities of the State and the State’s representatives.

  - “Proposal” means a written document that Contractor shall submit to the State in response to a Services Request Form, as further specified in Exhibit E.

  - “Reimbursable Expenses” means specific expense(s) incurred or to be incurred by Contractor and/or its Subcontractor(s) in pursuit of performance of the Work, as further specified in Work Orders.

  - “Service(s)” means and includes action(s) specified in a Work Order that shall be performed by the Contractor’s or its Subcontractor’s employees. Services may or may not result in the provision of Deliverables.

  - “Services Request Form” means a written document that the State shall submit to Contractor when requesting a Proposal, as further specified in Exhibit E.

  - The “State” refers to the Judicial Council of California / Administrative Office of the Courts (“AOC”).

  - “Statement of Work” “Statement of Work” means and includes a description of Services and Deliverables to be provided according to Work Order authorized according to this Agreement.

  - “State Standard Agreement” means the form used by the State to enter into agreements with other parties.  .

  - “Subcontractor” shall mean and include any individual, firm, partnership, agent, or corporation having a contract, purchase order, or agreement with the Contractor, or with any Subcontractor of any tier for the performance of any part of this Agreement.  When the State refers to Subcontractor(s) in this document, for purposes of this Agreement and unless otherwise expressly stated, the term “Subcontractor” includes, at every level and/or tier, all subcontractors, sub-consultants, agents, suppliers, and/or materialmen.

  - “Third Party” refers to any individual, association, partnership, firm, company, corporation, consultant, Subcontractor, or combination thereof, including joint ventures, that is not a party to this Agreement.

  - “Time and Materials Not to Exceed Basis” means that the Contractor shall be compensated for Work actually performed on an Hourly Basis, and, if specified in a Work Order, compensated separately for Expenses, but not in total to exceed the “Total Amount Encumbered to Date” for that Work Order.

  - “Travel and Living Expenses” means expenses for travel and living costs incurred or to be incurred by Contractor’s employees or Contractor’s Subcontractor’s employees in pursuit of performance of the Work, as further specified in Exhibit C.

  - “Work” means and includes the provision of Services alone and/or Services that result in the provision of Deliverables.

  - “Work Order” is a written document, substantially in the form of Exhibit E, that specifies the Work to be provided, the price of the Work, and any Expenses applicable to the performance of the Work, which, when signed by both Parties as specified in the  work order process of this Agreement becomes binding upon them.

- Manner of Performance of Work

##### Contractor shall provide, and shall act to ensure that its Subcontractors shall provide that all Work specified in these Contract Documents is performed to the State's satisfaction, in compliance with the standards specified in Exhibit D and in authorized Work Orders, and in compliance with the Nondiscrimination/No Harassment Clause, as set forth in this Exhibit B.

- Standard of Professionalism

##### Contractor shall conduct all Work consistent with professional standards for the industry and type of work being performed under the Agreement..

- Services Warranties

  - Contractor warrants and represents that its employees and its Subcontractors employees assigned to perform Services under this Agreement have the appropriate required credentials in the specified area(s) of competence required by the regulations cited in Exhibit D and/or an authorized Work Order, including having and maintaining appropriate licenses that meet State  requirements to professionally and diligently perform the work authorized. If no credentials are cited in Exhibit D or an authorized Work Order, they must have the skills, training, and background reasonably commensurate with his or her level of performance or responsibility so as to be able to perform in a competent and professional manner in accordance with generally accepted industry standards.

  - Contractor warrants that the Services provided hereunder will conform to the standards established by this Agreement and its authorized Work Orders.

  - All warranties, including any special warranties specified elsewhere herein, shall inure to the State, its successors, assigns, customer agencies, and any other recipients of the Services provided hereunder.

  - Contractor warrants that the Services will be performed on time and according to the applicable schedule or within the dates specified in Work Order(s).

  - Contractor warrants that the Services to be provided hereunder will conform to the requirements of the Statement of Work of this Agreement and as provided in the Work Orders authorized hereunder. This warranty shall begin upon the date of the State’s final payment for the Services provided under a Work Order, and shall extend for a period of 180 Days thereafter (“Warranty Period”). If the State identifies defect(s) in the Services provided during the Warranty Period, Contractor shall either re-perform the Services or otherwise remedy the defect to the satisfaction of the State. Contractor shall (unless a longer period is agreed to in writing with the State’s Project Manager) have a period of ten (10) Business Days following receipt of Notice of the existence of a defect, in which to provide a cure. In no event shall the State be responsible for any costs incurred by Contractor to remedy any deficiencies in the Services

  - All warranties, including any special warranties specified elsewhere herein, shall inure to the State, its successors, assigns, the Court(s), the Counties and/or any other customer agencies or other beneficiaries of the Services provided hereunder.

  - Contractor agrees that absent any material change to the specifications for the Work, Contractor shall provide all of the Work specified in the Work Order for the “Total Amount Encumbered to Date” applicable to the Work Order.

- Acceptance of Deliverables

  - The State’s Project Manager shall be responsible for the sign-off acceptance of all Deliverables required and performed/submitted pursuant to this Agreement. Upon successful completion of a Deliverable, Contractor shall provide the State’s Project Manager with a completed Acceptance and Signoff Form (Exhibit G). The State’s Project Manager will apply the standards established in Exhibit D and the authorized Work Order and the acceptance criteria set forth in subparagraph B of this article, as appropriate, to determine the acceptability of the Deliverable provided by Contractor.  If the State’s Project Manager rejects the Deliverable, the parties agree to any dispute(s) resulting from such rejection(s) will be resolved as set forth in this article.

  - Acceptance Criteria for Deliverables (“Criteria”) provided by Contractor pursuant to this Agreement include:

Timeliness:  The Work was provided on time; according to schedule;

Completeness:  The Deliverable contained all of the, Data, Materials, and features required by the Agreement and the Work Order; and

Technical accuracy:  The Deliverable complied with the standards of this Agreement and the Work Order, or, if this Agreement and the Work Order lack a standard for provision of the Work, the currently generally accepted industry standard.

  - Contractor shall provide the Deliverable to the State, in accordance with direction from the Project Manager and as provided for in Exhibit D and the authorized Work Order.  The State shall accept the Deliverable, provided that Contractor has delivered the Deliverable in accordance with the Criteria.   The State’s Project Manager shall assign the Acceptance and Signoff Form to notify Contractor of the Deliverable’s acceptability.

  - If the State rejects the Deliverable provided, the State’s Project Manager shall submit to Contractor’s Project Manager a written rejection describing in detail the failure of the Deliverable as measured against the Criteria.   If the State rejects the Deliverable, then Contractor shall have a period of ten (10) Business Days from receipt of the Notice of rejection to correct the stated failure(s) to conform to the Criteria.

  - If a resolution of the dispute is not reached between the State’s Project Manager and Contractor’s Project Manager as to the Deliverable’s acceptability, a principal of the Contractor and the Administrative Director of the AOC, or its designee, shall meet to discuss the problem.  If agreement cannot be reached, in the reasonable judgment of the Administrative Director of the AOC, or its designee, and/or the Contractor fails to cure such deficiencies that are perceived in the Deliverable to the reasonable satisfaction of the Administrative Director, or its designee, in the reasonable time established by the Administrative Director, the State may reject the Deliverable and will notify Contractor in writing of such action and the reason(s) for so doing.  Upon rejection of the Deliverable, the State may terminate this Agreement, or the individual Work Order applicable to said Deliverable, pursuant to the terms of Exhibit A - Standard Provisions article 3.

- Copyrights and Rights in Data, Material, and Deliverables

##### All copyrights and rights in any Data, Materials, and/or Deliverables produced with funding from this Agreement that may presumptively vest in Contractor shall be transferred to the State.

- Ownership

##### Any interest of Contractor or any of its Subcontractors in any Data, Materials, and/or Deliverables in any form, or other documents and/or recordings prepared by Contractor or its Subcontractors in its performance of Work under this Agreement shall become the property of the State.  Upon the State's written request, or upon any termination of this Agreement or any Work Order Contractor shall assign and/or shall act to ensure that its Subcontractor’s assign any such interest to the State and provide the State with copies of all such Data, Materials, and/or Deliverables, within thirty (30) Days of the request.

##### Contractor agrees and shall ensure that its Subcontractors agree not to assert any rights at common law, or in equity, or establish any claim to statutory copyright in such Data, Materials, and/or Deliverables. Contractor shall not, and shall ensure that its Subcontractors shall not publish or reproduce such Data, Materials, and/or Deliverables in whole, or part, or any manner or form, or authorize others to do so without the written consent of the State.

- Limitation on Publication

##### Contractor shall not, and shall ensure that its Subcontractors shall not publish or submit for publication any article, press release, or other writing relating to Contractor's services for the State without prior review and written permission by the State.

- Contractor's Personnel

  - Contractor shall provide all personnel and Subcontractor personnel necessary to provide the Work authorized under this Agreement.

  - Contractor and/or its Subcontractors shall provide certain Key Personnel, including Contractor’s Project Manager(s), to perform certain Work set forth in this Agreement and in Work Orders.

  - Contractor’s Project Manager shall:

Serve as the primary contact with the State’s Project Manager and personnel;

Manage the day to day activities of Contractor and its Subcontractor’s personnel;

Identify the appropriate resources needed;

Plan and schedule the Work;

Meet budget and schedule commitments;

Provide Progress Reports in accordance with this Agreement; and

Act to ensure the overall quality of the Work performed.

  - The State reserves the right to disapprove the continuing assignment of any Key Personnel provided under this Agreement, if, in the State's opinion, the performance of Key Personnel is unsatisfactory.  The State agrees to provide Notice to Contractor in the event it makes such a determination.  If the State exercises this right, Contractor shall immediately assign replacement Key Personnel, possessing equivalent or greater experience and skills.

  - If any of Key Personnel assigned to a Project, through no cause or fault of Contractor, become unavailable to perform Work, Contractor shall immediately provide replacement Key Personnel, possessing equivalent or greater experience and skills as required by this Agreement and as further specified in any resumes referenced in Work Orders.

  - Contractor shall ensure that the same Key Personnel named in Work Orders are retained during the performance of the Work of that Work Order.  However, Contractor may, with approval of the State’s Project Manager, introduce substitute Key Personnel with specific skill sets/qualifications, or release Key Personnel whose skill sets/qualifications are no longer needed, if advance approval in writing is received from the State’s Project Manager.

  - If any of the Key Personnel identified as specified in an authorized Work Order terminate their employment during the period of performance of a Work Order, Contractor will provide a substitute acceptable to the State's Project Manager.

  - If any Key Personnel become unavailable or are disapproved and Contractor cannot furnish a replacement acceptable to the State, the State may terminate this Agreement or the applicable Work Order for cause, pursuant to Exhibit A - Standard Provisions, article 3.

- Background Checks

  - If the Contractor assigns persons (whether employees, independent contractors, subcontractors or agents) to perform work under this Agreement that requires that the person have access to the systems (whether on-site or by remote access) or premises of the AOC or other Judicial Branch entities, the AOC shall have the right, but not the obligation, to conduct a background check or to require the Contractor to conduct a background check, as permitted by law, on all such persons before the AOC will grant to such persons access to the AOC’s or other judicial branch entities’ premises or systems.  The Contractor will cooperate with the AOC in performing such background check, and will promptly notify the AOC of any such person refusing to undergo such background check, and will reassign such person to perform other services.  The Contractor shall obtain all releases, waivers, or permissions required for the release of such information to the AOC.  Costs incident to background checks are the sole responsibility of the Contractor.

- Agreement Term and Renewals

  - The initial term of the Agreement shall commence on ______ and expire on May _.

  - The term of this Agreement may be extended for two additional one-year periods at the sole option of the State.

  - The parties agree that any extension of this Agreement is subject to a written Amendment.

  - This Agreement is of no force and effect until signed by both parties.  Any commencement of performance prior to execution of this Agreement by Contractor shall be at Contractor's own risk.

  - Regardless of the expiration date of this Agreement, the terms and conditions of this Agreement shall unless otherwise terminated as specified herein, continue to be binding upon any Work Order executed under this Agreement until the Work under said Work Order shall have been completed in full.

- Termination Other Than for Cause

  - In addition to termination for cause under Exhibit A, Standard Provisions, article 3, the State may terminate this Agreement or any Work Order for convenience and without cause at any time upon providing Contractor written Notice at least ten (10) Days before the effective date of termination.  Upon receipt of the termination Notice, Contractor shall promptly discontinue all Work affected unless the Notice specifies otherwise.

  - If the State terminates a Work Order authorized under this Agreement other than for cause, the State shall pay Contractor for the fair value of satisfactory Work rendered before the termination, not to exceed the Total Amount Encumbered to Date applicable to that Work Order.

- State's Obligation Subject to Availability of Funds

  - The State's obligation under this Agreement is subject to the availability of authorized funds.  The State may terminate the Agreement or any part of the Contract Work, without prejudice to any right or remedy of the State, for lack of appropriation of funds.  If expected or actual funding is withdrawn, reduced or limited in any way prior to the expiration date set forth in this Agreement, or in any Amendment hereto, the State may terminate this Agreement in whole or in part, upon written Notice to Contractor.  Such termination shall be in addition to the State's rights to terminate for convenience or default.

  - Payment shall not exceed the amount allowable for appropriation by Legislature.  If the Agreement is terminated for non-appropriation:

The State will be liable only for payment in accordance with the terms of this Agreement for Work provided prior to the effective date of termination; and

Contractor shall be released from any obligation to provide further services pursuant to the Agreement as are affected by the termination.

  - Funding for this Agreement beyond the current appropriation year is conditional upon appropriation by the Legislature of sufficient funds to support the activities described in this Agreement.  Should such an appropriation not be approved, the Agreement may terminate at the close of the current appropriation year.  The appropriation year ends on June 30 of each year.

- Notice:

  - Any Notice of breach required by or with regard to this Agreement shall be in writing and shall be delivered as follows:

  - Notice to the AOC shall be directed to:

##### Mr. Grant Walker

Senior Manager

Judicial Council of California

Administrative Office of the Courts – Business Services

455 Golden Gate Avenue

San Francisco, CA 94102

  - Notice to Contractor shall be directed to:

- Subcontracting

##### Contractor shall not subcontract the Work to be provided under this Agreement unless Contractor has identified the Subcontractor in writing in a Proposal that is acceptable to and authorized by the State in a Work Order.  No party to this Agreement shall in any way contract on behalf of or in the name of another party to this Agreement.

- Changes and Amendments

  - Changes or Amendments to any component of the Contract Documents, or to any authorized Work Order, can be made only with prior written approval from:

##### Mr. Grant Walker

##### Senior Manager

Judicial Council of California

Administrative Office of the Courts – Business Services

455 Golden Gate Avenue

San Francisco, CA 94102

  - Requests for said changes or Amendments must be submitted in writing and must be accompanied by a narrative description of the proposed change and the reasons for the change.  Additional funds may not be encumbered under the Agreement due to an act of Force Majeure, although the performance period of the Agreement may be amended due to an act of Force Majeure.   After a review of the request, a written decision shall be provided to Contractor.  Amendments to the Agreement and its Work Orders shall be authorized via bilateral execution of a State Standard Agreement.

  - Any terms and/or conditions specified in a Work Order that purport to modify or that conflict with the provisions of the Agreement shall be null and void, and without effect.

- Accounting System Requirement

##### Contractor shall maintain an adequate system of accounting and internal controls that meets Generally Accepted Accounting Principles or GAAP.

- Retention of Records

##### Contractor shall maintain all financial Data, supporting documents, and all other records relating to performance and billing under this Agreement for a period in accordance with California State and Federal law, a minimum retention period being no less than three (3) years.  The retention period starts from the date of the submission of the final payment request.  Contractor is also obligated to protect Data adequately against fire or other damage.

- Audit

  - Contractor shall permit the authorized representative of the State or its designee or both at any reasonable time to inspect or audit all Data relating to performance and billing to the State under this Agreement.  Contractor further agrees to maintain such Data for a period of three (3) years after final payment under this Agreement.

  - Such Data shall at a minimum include:

    - Contractor shall maintain a log and a file of time sheets for all authorized hours actually worked by Contractor’s employees and its Subcontractor’s employees under this Agreement.  The log must include, but is not limited to, the following information:  (1) name and title of the employee; (2) Subcontractor providing the employee, if applicable; (3) the dates and hours worked; (4) description of the Work performed; (5) hourly rate charged; and (6) Work Order Number of the Work Order under which the Work was performed. Upon the request of the State’s Project Manager, Contractor shall provide copies of the log and time sheets.

    - Contractor shall maintain a travel log and a file of original invoices for all authorized Travel and Living Expenses incurred by Contractor’s employees and its Subcontractor’s employees in performing the Work of this Agreement. The travel log must include, but is not limited to, the following information:  (1) the beginning and ending dates of the trip; (2) Subcontractor providing the employee, if applicable; (3) the name and title of the personnel making the trip; (4) the beginning location of the trip and the destination; (5) the purpose of the trip; and (6) Work Order Number of the Work Order under which said expenses were incurred.  Upon the request of the State’s Project Manager, Contractor shall provide copies of the log and invoices applicable to said expenses.

    - Contractor shall maintain a log and a file of original invoices for all authorized Reimbursable Expenses incurred by Contractor and its Subcontractors in performing Work authorized under this Agreement. The log must include, but is not limited to, the following information: (1) the party incurring the expenditure (Contractor or name of Subcontractor); (2) date of the expenditure; (3) the purpose of the expenditure; (4) description of the goods or services purchased; (5) the price of the expenditure; and (6) Work Order Number of the Work Order under which said expenses were incurred. Upon the request of the State’s Project Manager, Contractor shall provide copies of the log and invoices applicable to said expenses.

  - Upon the request of the State’s Finance Division or the State’s Project Manager, Contractor agrees to provide the logs of said Data pertaining to any particular Work Order requested, within 5 Business Days of request.

- Insurance and Waiver of Claims

  - General Requirements:

    - Contractor shall maintain insurance issued by an insurance company or companies that are rated “A-VII” or higher by A. M. Best’s key rating guide.  If self-insured, review of financial information may be required.

    - All coverage shall be in force until the end of the term of this agreement or Final Acceptance of the Work, whichever comes later.   If the insurance expires during the term of the Contract, the Contractor shall immediately provide a new current certificate or be declared in breach of Contract.  The State reserves the right to withhold all progress and retention payments until the breach is cured to the satisfaction of the State.  Renewal insurance certificates must be tendered to the State at least 10 days prior to the expiration of the previous insurance certificate.  This new insurance shall be in accordance with the terms of the Contract.

    - Insurance policies shall contain a provision that coverage will not be cancelled without 30 days prior written notice to the State.

    - The Contractor shall be responsible for any deductible or self-insured retention contained within the insurance.

    - In the event the Contractor fails to keep in effect at all times the specified insurance coverage, the State may, in addition to any other remedies it may have, terminate this Contract upon the occurrence of such event, subject to the provisions of this Contract.

    - Any insurance required to be carried shall be primary.

  - Insurance Requirements.  The Contractor shall furnish to the State evidence of insurance as follows:

    - Commercial General Liability: The Contractor shall maintain commercial general liability insurance written on an occurrence form covering the Contractor, the State parties, and subcontractors with limits of not less than $1,000,000 per occurrence and $2,000,000 aggregate.    The policy shall include coverage for liabilities arising out of premises, operations, independent contractors, products, completed operations, personal and advertising injury, and liability assumed under an insured contract.  This insurance shall apply separately to each insured against whom claim is made or suit is brought subject to the Contractor’s limit of liability.  The policy shall include the AOC and the State of California, its officers, agents, employees and servants as additional named insureds, but only insofar as the operations under the Contract are concerned.

    - Business Automobile Liability:    The Contractor shall maintain business automobile liability with limits of not less than $1,000,000 per accident.  Such insurance shall cover owned, hired, and non-owned motor vehicles.

    - Workers' Compensation:  The Contractor shall maintain statutory workers' compensation coverage for all its employees who will be engaged in the performance of the Contract, including special coverage extensions where applicable and employer’s liability with limits not less than $1,000,000 for each accident $1,000,000 disease policy limit, $1,000,000 disease – each employee, or $1,000,000 each occurence.

    - Professional Liability: Professional Liability/ Errors and Omissions insurance covering the contractor’s professional duty under this agreement with limits of at least $1,000,000 per claim and $1,000,000 in the annual aggregate. If the policy is written on a “claims made” reporting form, the contractor shall keep such policy in force (or purchase an extended reporting period) for not less than three years from the date of completion of the Work which is subject in this Agreement. The retroactive date of any such “claims made” policy must be no greater than the date the activities commenced pursuant to this Agreement.

  - Waiver of Claims: The State, the Judicial Council of California, the Administrative Office of the Courts, the superior courts and appellate courts of the State of California, and any of their officers, employees, and agents (collectively, "State Entities") shall not be liable for any injury, loss, or damage to Contractor, Subcontractors, or their officers, employees, or agents including, without limitation, damage to the property of Contractor, Subcontractors or their officers, employees, and agents, by or from any cause whatsoever, except to the extent the injury, loss, or damage was caused from the gross negligence or intentional misconduct of the State Entities.  Contractor and Subcontractors hereby waive all claims and their respective insurers waive all rights of subrogation against the State Entities for any injury, loss, or damage to Contractor, Subcontractors, or their officers, employees, or agents including, without limitation, damage to the property of Contractor, Subcontractors or their officers, employees, and agents, in or about the Facilities, by or from any cause whatsoever, except to the extent the injury, loss, or damage was caused from the gross negligence or intentional misconduct of the State Entities. Neither the State, nor any officer or employee of the State, shall be liable for any loss or damage that may happen to the Work, or any part thereof; nor to any of the materials or other items used or employed in performing the Work;

  - NO PERSONAL LIABILITY:  Neither the State, nor any other officer or employee of the State will be personally responsible for liabilities arising under the Contract.

- Confidentiality

  - Both the State and Contractor acknowledge and agree that in the course of performing the Work under this Agreement, the State may disclose Confidential Information to Contractor and/or its Subcontractors.

  - Contractor agrees not to disclose the Confidential Information to any Third Party and to treat it with the same degree of care as it would its own confidential information.  It is understood, however, that Contractor may disclose the State’s Confidential Information on a “need to know” basis to Contractor’s employees and Subcontractors and, as directed by the Project Manager, representatives of the State that are performing Work authorized under this Agreement.  All such employees and Subcontractors of Contractor shall have executed a confidentiality agreement with Contractor requiring a promise of confidentiality concerning Contractor’s clients and business.

  - Contractor shall acquire no right or title to the Confidential Information.  Contractor agrees not to use the Confidential Information for any purpose except as contemplated pursuant to this Agreement.  Notwithstanding the foregoing, Contractor may disclose the Confidential Information (i) to the extent necessary to comply with any law, rule, regulation or ruling applicable to it; (ii) as appropriate to respond to any summons or subpoena applicable to it; or (iii) to the extent necessary to enforce its rights under this Agreement.

  - The State reserves the right to disclose all Work provided under this Agreement disclose to third parties for the purpose of validation of the Work.

  - Contractor shall bind its Subcontractors to provisions of confidentiality  with regard to the Confidential Information disclosed that are not less strict than those assumed by Contractor hereunder.

- Trade Secret, Patent and Copyright Indemnification

(Option 4)

  - Contractor shall hold the Court(s), the State, its officers, agents, and employees, harmless from liability of any nature or kind, including costs and expenses, for infringement or use of any copyrighted or un-copyrighted composition, secret process, patented or un-patented invention, article, or appliance furnished or used by Contractor or its Subcontractors in connection with this Agreement.

  - Contractor, at its own expense, shall defend any action brought against the Court(s) and/or the State, its officers, agents, and employees, to the extent that such action is based upon a claim that any Deliverable(s), Data or Materials supplied by Contractor or its Subcontractors infringes a United States patent or copyright or violates a trade secret.  Contractor shall pay those costs and damages finally awarded against the Courts and/or the State its officers, agents, and employees, in any such action.  Such defense and payment shall be conditioned on the following:

That Contractor shall be notified within a reasonable time in writing by the State of any Notice of such claim; and,

That Contractor shall have the sole control of the defense of any action on such claim and all negotiations for its settlement or compromise, provided, however, that when principles of government or public law are involved, the Court(s) and/or the State shall have the option to participate in such action at its own expense.

  - Should the Deliverable(s), Data, Materials, become, or in Contractor’s opinion are likely to become, the subject of a claim of infringement of a United States patent or copyright or a trade secret, the State shall permit Contractor at its option and expense either to procure for the Court(s) and/ or the State the right to continue using the Deliverable, Data or Materials, or to replace or modify the same so that they become non-infringing.  If none of these options can reasonably be taken, or if the use of such Deliverables, Data or Materials by the Courts and/or the State shall be prevented by injunction, Contractor agrees to take back such Deliverables, Data or Materials and make every reasonable effort to assist the Courts and/or the State in procuring substitute Deliverables, Data or Materials.  If, in the sole option of the State, the return of such infringing Deliverables, Data or Materials makes the retention of other Deliverables, Data or Materials acquired from Contractor under this Agreement impractical, the State shall then have the option of terminating the applicable Work Order(s), or applicable portions thereof, or this Agreement in its entirety, without penalty or termination charge.  Contractor agrees to take back such Deliverables, Data or Materials and refund any sums that the State has paid Contractor less any reasonable amount for use or damage.

  - The foregoing states the entire liability of Contractor to the Courts and/or the State with respect to infringement of patents, copyrights, or trade secrets.

- Permits and Licenses

##### The Contractor shall observe and comply, and shall ensure that it Subcontractors observe and comply with all federal, state, city, and county laws, rules, and regulations affecting Contractor and its Subcontractor(s) performance of the Work provided under this Agreement.  The Contractor shall procure and keep in full force and effect, and shall ensure that it Subcontractors procure and keep in full force and effect, during the Term of this Agreement, all permits and licenses necessary to accomplish the Work contemplated in this Agreement.

- Conflict of Interest

  - Contractor shall ensure that its officers and employees shall not participate in proceedings that involve the use of State funds or that are sponsored by the State if the person's partner, family, or organization has a financial interest in the outcome of the proceedings.  Contractor and its officers and employees shall also avoid actions resulting in or creating the appearance of (1) use of an official position with the government for private gain; (2) preferential treatment to any particular person associated with this Agreement or the Work of this Agreement; (3) loss of independence or impartiality; (4) a decision made outside official channels; or (5) adverse effects on the confidence of the public in the integrity of the government or this Agreement. Contractor agrees that it shall bind its Subcontractors to conflict of interest provisions not less strict than those provided here.

  - Contractor shall certifies and shall require its Subcontractors to certify that:

# Former State employees will not be awarded a contract for (a) two (2) years from the date of separation if that employee had any part in the decision making process relevant to this Agreement, or (b) for one (1) year from the date of separation if that employee was in a policy making position in the same general subject area as this Agreement within the twelve (12) month period of his or her separation from State service.

- Covenant Against Gratuities

##### Contractor warrants by signing this Agreement that no gratuities, in the form of entertainment, gifts, or otherwise, were offered by Contractor or any agent, director, Subcontractor or representative of Contractor, to any officer, official, agent, or employee of the State with a view toward securing this Agreement or securing favorable treatment with respect to any determinations concerning the performance of this Agreement.  For breach or violation of this warranty, the State will have the right to terminate this Agreement, either in whole or in part, and any loss or damage sustained by the State in procuring, on the open market, any Work which Contractor agreed to supply, which shall be borne and paid for by Contractor.  The rights and remedies of the State provided in this provision shall not be exclusive and are in addition to any other rights and remedies provided by law or under this Agreement.

- National Labor Relations Board

##### By executing this Agreement, Contractor certifies under penalty of perjury under the laws of the State of California that no more than one (1) final, unappealable finding of contempt of court by a federal court has been issued against Contractor within the immediately preceding two (2) year period because of Contractor's failure to comply with an order of the National Labor Relations Board.

- Drug-Free Workplace

##### Contractor certifies that it will provide a drug-free workplace as required by California Government Code, Sections 8355 through Section 8357.

- Nondiscrimination/No Harassment Clause

  - During the performance of this Agreement, Contractor and its Subcontractors shall not unlawfully discriminate against any employee or applicant for employment because of race, religion, color, national origin, ancestry, physical or mental disability, medical condition, marital status, age (over 40), sex, or sexual orientation.  Contractor shall ensure that the evaluation and treatment of employees and applicants for employment are free of such discrimination.

  - During the performance of this Agreement, Contractor and its Subcontractors shall not engage in unlawful harassment, including sexual harassment, with respect to any persons with whom Contractor or its Subcontractors interact in the performance of this Agreement.  Contractor and its Subcontractors shall take all reasonable steps to prevent harassment from occurring.

  - Contractor shall comply and shall ensure that its Subcontractors comply  with applicable provisions of the Fair Employment and Housing Act, California Government Code, Sections 12990 et seq., and the applicable regulations promulgated under California Code of Regulations, title 2, Sections 7285 et seq.  The applicable regulations of the Fair Employment and Housing Commission implementing California Government Code, Section 12990, set forth in chapter 5 of division 4 of title 2 of the California Code of Regulations, are incorporated into this Agreement by reference and made a part of it as if set forth in full.

  - Contractor and any of its Subcontractors shall give written Notice of their obligations under this clause to labor organizations with which they have a collective bargaining or other agreement.

  - Contractor shall include the nondiscrimination/no harassment and compliance provisions of this clause in any and all subcontracts issued to its Subcontractors to perform Work under the Agreement.

- Americans with Disabilities Act

##### By signing this Agreement, Contractor assures the State that it complies with applicable provisions of the Americans with Disabilities Act (“ADA”) of 1990 (42 U.S.C. Sections 012101 et seq.), which prohibits discrimination on the basis of disability, as well as with all applicable regulations and guidelines issued pursuant to the ADA.

- California Law

##### This Agreement shall be governed by California law without regard to any conflict of law rules that would direct the application of the laws of any other jurisdiction.  The Contractor irrevocably consents to personal jurisdiction in California.

- Severability

##### If any term or provision of this Agreement is found to be illegal or unenforceable, this Agreement shall remain in full force and effect and that term or provision shall be deemed stricken.

- Waiver

##### The omission by either party at any time to enforce any default or right, or to require performance of any of this Agreement's terms, covenants, or provisions by the other party at the time designated, shall not be a waiver of the default or right, nor shall it affect the right of the party to enforce those provisions later.

- Signature Authority

##### The parties signing this Agreement certify that they have proper authorization to do so.

- Survival

##### The termination or expiration of the Agreement shall not relieve either party of any obligation or liability accrued hereunder prior to or subsequent to such termination or expiration, nor affect or impair the rights of either party arising under the Agreement prior to or subsequent to such termination or expiration, except as expressly provided herein.

- Entire Agreement

##### This Agreement, consisting of all documents as defined herein, constitutes the entire agreement between the parties with respect to the subject matter hereof and shall supersede all previous proposals, both oral and written, negotiations, representations, commitments, writing and all other communications between the parties.  No waiver, alteration, modification of, or addition to the terms and conditions contained herein shall be binding unless expressly agreed in writing by a written amendment to this Agreement.

- END OF EXHIBIT

EXHIBIT C

WORK ORDER AUTHORIZATION PROCESS

- and

- PAYMENT PROVISIONS

  - Work Order and Contract Amounts

  - The total amount the State may pay to Contractor under any individual Work Order authorized this Agreement for performing all Work, as well as all Travel and Living Expense and/or Reimbursable Expenses specified therein, shall not in any event exceed the Total Amount Encumbered to Date specified on the face of the Work Order Authorization Form applicable to that Work Order.

  - The total amount the State may pay to Contractor under this Agreement (“Contract Amount”) shall not in any event exceed the total of all Total Amount(s) Encumbered to Date on all Work Orders authorized under this Agreement.

  - Work Order Authorization Process

  - The State will authorize the performance of Work and spending of funds under this Agreement via written Work Order(s) which shall be substantially in the format provided in Exhibit E and authorized as specified in this Work Order process.

  - The State’s Project Manager will provide Contractor with an unsigned Services Request Form, describing the Work the State desires to purchase. The State will complete the parts of the form designated as “State to Complete”. The State shall describe in full the Services requested, including the location(s) at which they will be performed, as well as the requested beginning and end dates for the Work. The State’s Project Manager will designate whether the Work requested shall be performed on a Deliverable Basis. The State’s Project Manager will designate whether the Work requested shall be paid for on a Fixed Price Basis or a Time and Materials Not to Exceed Basis. When complete, the State’s Project Manger will submit the unsigned Services Request Form to Contractor’s Project Manager via e-mail.

  - Upon receipt, Contractor will, based upon the Services requested by the State modify the Services Request Form, changing its title to “Proposal” and shall, in coordination with and with the agreement of the State’s designated Project Manger:

    - Assign and Provide Name and Address information of the Contractor’s Project Manager who will be assigned to this Work Order.

    - Provide a Statement of Work. Provide a narrative work plan specifying the responsibilities of the parties and the Key Personnel with regard to performance of the Work, including any assumptions and/or conditions applicable to performance of the Work

    - If agreed to, provide revised start and completion dates for the Work, or provide a detailed Project Schedule detailing the critical path responsibilities for the Project.

    - Provide a list of Key Personnel who will be assigned to perform the Work. Identify any Subcontractor personnel as such.

    - In the Price area of the form:

- a.	If the Services have been requested on a Deliverables Basis and a Fixed Price Basis, provide a description of the Services pertaining to each individual Deliverable along with the name of the Deliverable and a Firm Fixed Price for that Deliverable. If more than one Deliverable is requested, provide a grand total (“Grand Total”) of all Deliverables for the Work Order. Provide a schedule naming the Deliverables and identifying the Fixed Price to be paid for each Deliverable.

- b.	If the Services have been requested on a Deliverables Basis and a Time and Materials Not to Exceed Basis, provide a description of the Services pertaining to each individual Deliverable along with the name of the Deliverable and the name(s) and title(s) of Key Personnel that will perform the Services, their expected hours of Work, their applicable Hourly Rates, and total expected amount to be paid for each employee. Describe any expected Travel and Living Expenses that are expected to be incurred in pursuit of providing the Deliverable, using the AOC Travel and Living Expense Guidelines to cost out the Travel and Living Expense. Describe any Reimbursable Expenses that are expected to be incurred in pursuit of providing the Deliverable. Provide a total, for each Deliverable, including the cost of all Work to be performed on an Hourly Basis, all expected Travel and Living Expense, and all expected Reimbursable Expense. Provide a Grand Total of all Deliverables for the Work Order.

- c.	If the Services have been requested on a Time and Materials Not to Exceed Basis but not on a on a Deliverables Basis, provide a description of the Services and the name(s) and title(s) of Key Personnel that will perform the Services, their expected hours of Work, their applicable Hourly Rates, and total expected amount to be paid for each employee. Describe any expected Travel and Living Expenses that are expected to be incurred in pursuit of providing the Services, using the AOC Travel and Living Expense Guidelines to cost out the Travel and Living Expense. Describe any Reimbursable Expenses that are expected to be incurred in pursuit of providing the Work. Provide a Grand Total of the Hourly Work, Travel and Living Expense, and Reimbursable Expense(s) applicable to the Work Order.

    - Upon completion of the above, Contractor shall submit the unsigned Proposal to the AOC’s Project Manager via e-mail.

    - Contractor Proposals so submitted are not be revocable for 20 Business Days following the day received by the State, or until the date scheduled for the start of the Work in the applicable Work Order, whichever event occurs sooner.

  - If the State wishes to accept the Proposal and  proceed with the Work, the State will notify the Contractor and shall provide via e-mail a Work Order consisting of the then current format of the State Standard Agreement Form 220 (Exhibit F ) authorizing the Proposal in the full amount specified in the Proposal and referencing the Proposal.

  - Contractor shall sign two originals of the Work Order, which shall be sent to the State at following address:

- George Santore

- Senior Contract Specialist

- Business Services, Floor 7

- Administrative Office of the Courts

- 455 Golden Gate Ave.

- San Francisco, CA 94102

  - Upon receipt, the State shall, if it chooses to proceed with authorization of the Work Order, countersign both originals and return one original to the Contractor.

  - Upon countersignature by the State, the Work Order shall, for the purposes of this Agreement, be considered authorized, and shall be binding upon the parties.

  - Upon receipt of a signed Work Order, Contractor is authorized to begin the Work when and as specified in said Work Order.

  - If the parties agree to revise an existing Work Order, the parties agree that such revisions are subject to the authorization of a revision to be performed in the same manner as authorization of the Work Order itself. Upon authorization, the revised Work Order shall supersede and override the existing Work Order.

  - The State reserves the right to modify the forms provided in Exhibit F, as it deems necessary or appropriate, in its sole discretion, and will notify Contractor of any modification to said form prior to implementing the modified form(s).  Any such modification(s) will be incorporated into this Agreement by an Amendment.

  - Any commencement of Work and any expenditure made prior to Contractor’s receipt of a signed Work Order shall be made at Contractor’s sole risk.

  - The State’s Project Manager named on the individual Work Order(s) shall monitor and evaluate Contractor's performance. All requests and communications between the State and the Contractor regarding the Work must make through the State’s designated Project Managers.

  - There is no limit on the number of Work Orders the State may issue under this Agreement.

  - There will be no specific limitation on the minimum and/or maximum amount authorized under an individual Work Orders.

  - The State does not guarantee that Contractor will receive any Work Order(s) under this Agreement.

  - Compensation:

    - Compensation for Types of Work Orders

      - Fixed Prices Work Orders Provided on a Deliverables Basis

When a Work Order specifies that the Work is to be provided on a Deliverables Basis and Contractor is to be compensated on a Fixed Price Basis, Contractor shall be compensated solely at the actual Fixed Price(s) specified for the Deliverables in said Work Order.

      - Time and Materials Not to Exceed Basis Work Orders Provided On a Deliverables Basis

When a Work Order specifies that the Work is to be provided on a Deliverables Basis and Contractor is to be compensated on a Time and Materials Not to Exceed Basis, Contractor shall be compensated at the Hourly Rates for Services as specified below, plus Travel and Living Expenses as specified below, plus Reimbursable Expenses as specified below.

      - Time and Materials Not to Exceed Work Orders Not Provided on a Deliverables Basis

When a Work Order specifies that the Work is not to be provided on a Deliverables Basis and Contractor is to be compensated on a Time and Materials Not to Exceed Basis, Contractor shall be compensated for Work provided at the Hourly Rates for Services as specified below, plus Travel and Living Expenses as specified below, plus Reimbursable Expenses as specified below in an amount up to but not exceeding the “Total Amount Encumbered to Date” applicable to the Work Order.

    - Hourly Rates for Services

When, as specified in an authorized Work Order, Contractor is to be compensated on an Hourly Basis, Contractor shall be compensated only for hours actually incurred by Contractor or its Subcontractor employees in pursuit of the Work. Contractor shall be compensated at the Hourly Rates applicable to Contractor’s employees as specified below, or at lower rates if so agreed to and specified in a Work Order. Hourly Rates for any Contractor’s Subcontractor employees shall be as specified in the Work Order, are subject to AOC agreement on a Work Order by Work Order basis, and shall only apply to the Work Order in which authorized.

Title			Hourly Billing Rate

1.  Managing Principal		$______

2.  Principal/Director		$______

3.  Associate/Sr. Project Manager	$______

4.  Project Manager		$______

5.  Project Engineer		$______

6.  Specifications Writer / Estimating / Scheduling	$______

7.  Administrative Support 		$______

    - Compensation for Travel and Living Expenses:

- If an authorized Work Order specifies that Contractor is to be compensated for Travel and Living Expenses, Contractor shall be compensated according to the following AOC Policy for Compensation for Travel and Living Expenses:

      - The State shall reimburse Contractor for actual and reasonable transportation, meals, and lodging expenses actually incurred by Contractor’s and its Subcontractor’s employees in the course of their performance of the Work, but subject to the following:

        - If air transportation is authorized, the State will reimburse Contractor only at the actual cost incurred.  All air transportation is limited to coach fares and must be booked a minimum of fourteen (14) Days prior to travel, unless the Project Manager agrees to a shorter period in the Work Order.

        - If overnight lodging expense is authorized, in accordance with the California Victim Compensation and Government Claims Board (formerly State Board of Control) guidelines, the State will reimburse Contractor only (i) for hotel room rental at the actual cost not to exceed current, applicable GSA rates per Day, plus occupancy tax and/or energy surcharge; and (ii) for meals, at the actual cost not to exceed the following maximum amounts per person per Day:  breakfast~$6.00; lunch~$10.00; dinner~$18.00; and incidentals~$6.00.

        - If private vehicle ground transportation expense is authorized, the State will reimburse Contractor at $0.55 cents per mile.

        - The State is not obligated to pay for, and Contractor shall not invoice for any hours of non-production work expended by the Contractor or its Subcontractor’s employees that are spent traveling to or from the location where the Work is performed.

        - Travel and Living Expenses shall be billed to the State at Contractor’s actual cost, including any discounts or rebates accorded to Contractor or its Subcontractors, and are not subject to any markup, fee, or other charge.

    - Compensation for Reimbursable Expenses:

- If an authorized Work Order specifies that Contractor is to be compensated for Reimbursable Expenses, Contractor shall be compensated as follows:

      - The State shall reimburse Contractor for said expenses. Reimbursable Expenses shall not, exceed the total estimated amount for said expenses specified in the Work Order.

      - Reimbursable expenses are limited to itemized expenses otherwise not expressly excluded under this Agreement that are clearly and specifically identified in a Work Order, for goods or services necessary to the performance of the Work and actually incurred by Contractor and or its Subcontractors or their respective employees in the performance of the Work.

      - Reimbursable Expenses shall be billed to the State at Contractor’s or its Subcontractor’s actual cost, including any discounts or rebates accorded to Contractor or its Subcontractors, and are not subject to any markup, fee, or other charge.

    - Taxes

- The State is exempt from federal excise taxes and no payment will be made for any taxes levied on Contractor’s or any Subcontractor’s employees’ wages.  The State will pay for any applicable State of California or local sales or use taxes on the Deliverables provided or Services rendered pursuant to this Agreement.

  - Invoicing Requirements

- Contractor shall invoice the State once monthly, with separate invoice for each Work Order summarizing all payments due under that Work Order in the previous calendar month.

- Contractor shall submit one (1) original and two (2) copies of invoices to:

###### Judicial Council of California

###### Administrative Office of the Courts

###### c/o Finance Division, Accounts Payable

###### 455 Golden Gate Avenue, 7th Floor

###### San Francisco, CA 94102-3660

- Contractor shall simultaneously submit another copy of the invoice to the State Project Manager named on the Work Order at the address specified for that Project Manager on the Work Order.

- For Fixed Prices Work Orders Provided on a Deliverables Basis, Contractor shall invoice on successful acceptance of a Deliverable. Contractor’s invoice(s) shall clearly specify:

- The Contract number;

- The Work Order Number provided on the Work Order.

- A unique invoice number;

- Contractor’s name and address;

- Contractor’s Taxpayer identification number (FEIN);

- Description of the Deliverable as specified in the Work Order

- The Fixed Price of the Deliverable

- Preferred remittance address, if different from the mailing address

- The DVBE dollars expended, if DVBE commitments were made.

- For Time and Materials Not to Exceed Basis Work Orders Provided On a Deliverables Basis, Contractor shall invoice on successful acceptance of a Deliverable. Contractor’s invoice(s) shall clearly specify:

- The Contract number;

- The Work Order Number provided on the Work Order.

- A unique invoice number;

- Contractor’s name and address;

- Contractor’s Taxpayer identification number (FEIN);

- For each Deliverable accepted in the previous calendar month, provide separately by Deliverable:

- Description of the accepted Deliverable, as specified in the Work Order

- Names, Titles, Hours, Rates and Dates of Performance for all of Contractor or its Subcontractor employees for hours of Work actually incurred in providing that Deliverable during the previous calendar month, including a total for all such Work.

- If the Work Order specifies that the Contractor is to be compensated for Travel and Living Expenses incurred in providing that Deliverable, the dates the expense was incurred, name of employee, and separate costs for air transportation, overnight lodging, private vehicle ground transportation (include origin, destination, and miles claimed).

- If the Work Order specifies that the Contractor is to be compensated for Reimbursable Expenses incurred in providing that Deliverable, the date the expense was incurred, description of the expense, and amount of the expense.

- A grand total for all hours, Travel and Living Expenses, and Reimbursable Expenses billed on the invoice, individually for each Deliverable and in total for the invoice, with a grand total

- Preferred remittance address, if different from the mailing address

- The DVBE dollars expended, if DVBE commitments were made.

- For Time and Materials Not to Exceed Basis Work Orders Not Provided On a Deliverables Basis, Contractor shall invoice as follows. Contractor’s invoice(s) shall clearly specify:

- The Contract number;

- The Work Order Number provided on the Work Order.

- A unique invoice number;

- Contractor’s name and address;

- Contractor’s Taxpayer identification number (FEIN);

- Names, Titles, Hours, Rates and Dates of Performance for all of Contractor or its Subcontractor employees for hours of Work actually incurred during the previous calendar month, including a total for all such Work.

- If the Work Order specifies that the Contractor is to be compensated for Travel and Living Expenses, the dates the expense was incurred, name of employee, and separate costs for air transportation, overnight lodging, private vehicle ground transportation (include origin, destination, and miles claimed).

- If the Work Order specifies that the Contractor is to be compensated for Reimbursable Expenses, the date the expense was incurred, description of the expense, and amount of the expense.

- A grand total for all hours, Travel and Living Expenses, and Reimbursable Expenses billed on the invoice.

- Preferred remittance address, if different from the mailing address

- The DVBE dollars expended, if DVBE commitments were made.

  - Payment

    - The AOC will endeavor to pay invoices within sixty (60) days after receipt of a correct, itemized invoice. In no event shall the AOC be liable for interest or late charges for any late payments.

    - Payment shall be made by the AOC to the Contractor at the address specified on the invoice.

    - The AOC may withhold full or partial payment to the Contractor in any instance in which the Contractor has failed or refused to satisfy any material obligation provided for under this Agreement or the Work Order.

  - Disallowance

If the Contractor claims or receives payment from the AOC that is later disallowed by the AOC, the Contractor shall promptly refund the disallowed amount to the AOC upon the AOC’s request.  At its option, the AOC may offset the amount disallowed from any payment due or that may become due to the Contractor under this Agreement or any other agreement.

  - Payment Does Not Imply Acceptance of Work

The granting of any payment by the AOC, or the receipt thereof by the Contractor, shall in no way lessen the liability of the Contractor to correct unsatisfactory work in connection with this Agreement.

  - Release of Claims

The acceptance by the Contractor of its final payment due under this Agreement shall be and shall operate as a release to the State and the AOC of all claims and all liability to the Contractor for everything done or furnished in connection with this Agreement (including every act and neglect of the AOC), with the exception of any claims that are expressly identified by the Contractor as outstanding as of the date of Contractor’s submission of Contractor’s final application for payment.  Contractor’s failure to identify any such claims shall operate as a release of all claims.

END OF EXHIBIT

EXHIBIT D

STATEMENT OF WORK

- 1.	Project Description

- Contractor shall, as authorized, provide the Services specified in this statement of work (“Statement of Work”, “SOW”) and as may be further specified in Statement of Work specified in Work Orders authorized under this Agreement

- 2.	Schedule Of Work

The dates of performance and schedule applicable to the provision of the Work under this Agreement will be provided in authorized Work Order. Contractor agrees that it shall provide the Services of the specified Work Order within the dates of performance and according to said schedule.

- 3.	Statement of Work for Program Management

Contractor agrees to provide or perform, as specified in this Agreement, the following Services and tasks set forth in this section and as further elaborated in Work Orders when authorized under this Agreement, as well as any other services that are necessary, normal, customary, or incidental to the performance of Contractor’s responsibilities.  Work Orders may contain additional terms and conditions regarding the Work that are applicable only to the Work Order in which authorized, however, no provision of a Work Order may act to modify or may conflict with the terms and conditions of this Agreement.

3.1	Basic Services for Program Management:

Service Provider to provide program management services for the SB 1407 capital courthouse construction program in California on an as-needed basis.  Types of projects included in the SB 1407 program are new construction and major renovation projects.  The Service Provider may be asked to provide a program management professional(s) to act as a key management and technical consultant to the AOC/OCCM on program-wide management, implementation, and technical issues.  In general, the Service Provider may be called upon to provide program-wide services including, but not be limited to overall program management, program review and evaluation, cost estimating, program scheduling and analysis, and program reports.  The Service Provider will report directly to a designated AOC/OCCM Assistant Director for assignments, direction, and guidance.  As a Service Provider for program management, the following services may be required:

- Manage program to ensure that key program management team staff and functions are operating properly and communicating regularly.

- Monitor, document, and present program activities to ensure that the program status and direction are clearly and accurately understood by stakeholders, courts, governing agencies, interested third parties, and the public at large.

- Provide program leadership and foster a culture of innovation, excellence, collaboration, and mutual support among the program management and project management teams.

- Working with AOC/OCCM financial manager, monitor program cash flow to ensure that required funds are available when needed.

- Work with regional project management teams of the program to achieve economies of scale.

- Oversee development and updates of a master program schedule and execution of the timing of the program according to the schedule’s critical path requirements.

- Refine, develop where required, and implement processes and procedures for planning and delivering individual projects and ensure they are and working effectively.

- Monitor and ensure that the lessons learned process is viable and effective.

- Monitor and ensure that project teams have adequate program-level support resources and serve as arbiter of difficult or complex resourse allocation situations.

  - In Addition the Service Provider for Program Management Shall:

- Provide all necessary expertise and services and to have and maintain appropriate licenses that meet State  requirements to professionally and diligently prosecute the work authorized.

- Contract for or employ at Service Provider's expense, subcontractors to the extent deemed necessary for the work.

- Consult with normal and customary employees, agencies, and/or representatives of the State regarding the work of each Work Order.  These include but not limited to AOC’s division and unit partners such as the Facilities Management Unit, Office of Emergency Response Services, Information Technology Unit, and Audio Visual Unit.

- Update the Program Management Plan as required as the program progresses.

- Prepare and issue Monthly Program Progress Reports summarizing progress and identifying issues of concern using the format and content requirements provided by AOC/OCCM.

- Attend meetings with the State, court, other professionals employed by the State and local and regional agencies as needed and directed to perform the work.

- Prepare and issue meeting minutes documenting decisions and required action items for program management meetings attended.

- Work effectively with other State agencies, including but not limited to Division of the State Architect, State Fire Marshall, and Corrections Standards Authority in integrating their requirements into the SB 1407 program.

- Abide by all regulations imposed by funding sources, such as auditing requirements and payroll affidavits.

- Provide a professional level of review of all deliverables to assure quality, technical accuracy, and the coordination of all work and documents furnished by Service Provider under this Agreement.  Service Provider shall, without additional compensation, correct or revise any errors in its work or documents.

- Statement of Work for Project and/or Construction Management

Contractor agrees to provide or perform, as specified in this Agreement, the following Services and tasks set forth in this section and as further elaborated in Work Orders when authorized under this Agreement, as well as any other services that are necessary, normal, customary, or incidental to the performance of Contractor’s responsibilities.  Work Orders may contain additional terms and conditions regarding the Work that are applicable only to the Work Order in which authorized, however, no provision of a Work Order may act to modify or may conflict with the terms and conditions of this Agreement.

4.1	Basic Services for Project and Construction Management:

Service Provider to provide project and/or construction management services on various SB 1732 and SB 1407 court facility projects in California on an as-needed basis.  Types of projects include new construction, major renovation projects and modification projects of existing facilities.  The Service Provider may be requested to provide full and comprehensive project management services with personnel who maintain appropriate licenses that meet State  requirements who professionally and diligently prosecute the work authorized  on specific, major new facility projects or partial services on any defined component of the process.  In general, the Service Provider may be called upon to provide services including, but not be limited to, project management, project design review and evaluation, cost estimating, value engineering, bid evaluation, project scheduling and analysis, cost-benefit analyses, constructability reviews, project reports, peer reviews, claims analysis and negotiation, construction inspection, and/or general construction management of a construction project.  Should the Service Provider be asked to perform as project manager representing the AOC/OCCM on a given project, the consulting Service Provider’s role and responsibility will be typical of that performed by an owner’s representative in project management and construction management activities.  In these instances, the Service Provider will report directly to a designated AOC/OCCM Manager, Project Director, or Project Manager for project assignments, direction, and guidance.  As a Service Provider project manager, the following services may be required for each phase of the project:

  - Site Selection and Acquisition Phase:

- Prepare initial Project Management Plan using the format and content requirements provided by AOC/OCCM and review and execute with the court and other principal project participants.

- Develop and analyze the overall master project schedule and comment and advise the AOC/OCCM and court on the master schedules contents and time frames.

- Participate in and contribute to the A/E selection process for the project.

- Prepare the A/E scope of services and negotiate fees.

- Monitor and facilitate project approvals with the Department of Finance (DOF) and State Public Works Board (SPWB).

- Coordinate and facilitate site selection and acquisition activities with the court and other AOC departments (i.e., Office of Emergency Response Services (OERS)) and AOC/OCCM units (Real Estate and Asset Management (REAM) and Business and Planning (B&P).

- Coordinate due diligence activities.

  - Preliminary Plans Phase (Schematic Design and Design Development):

- Organize, implement, participate in, and contribute to the selection process for the construction manager at risk (CM@Risk) or other project delivery method general contractor.

- Manage, coordinate and participate fully in the design process working with the court, AOC/OCCM, other AOC divisions, and all contracted consultants to ensure that the design meets the requirements specified in the applicable, authorized Project Feasibility Report (PFR), Capital Outlay Budget Change Proposal (COBCP), and Trial Court Facility Standards.

- Review in detail all design documents prepared by the commissioned A/E firm and make recommendations to insure that the finished facility will conform to the Trial Court Facilities Standards and will be acceptable to the court.

- Review and provide input as to the technical quality of the design documents and make recommendations for their improvement.

- Revise and update the overall master project schedule and comment and advise the AOC/OCCM and court on the master schedules contents and time frames.

- Review and comment on the cost estimates developed at the end of both Schematic Design and Design Development sub-phases and prepared by both the A/E and CM@Risk firms and participate in cost control management of the project to insure that the project can be constructed for the authorized budget amount.

- Participate in and contribute to value engineering and value analysis exercises as required.

- Coordinate and contribute to constructability and peer reviews of the project.

- Prepare Department of Finance (DOF) and State Public Works Board (SPWB) documents and monitor and facilitate their approvals.

  - Working Drawings Phase (Working Drawings and Bidding):

- Review in detail contract documents (construction drawings and specifications) prepared by the commissioned A/E firm and make recommendations to insure that the finished facility will conform to the Trial Court Facilities Standards and will be acceptable to the court.

- Review and provide input as to the technical quality of the contract documents and make recommendations for their improvement.

- Revise and update the overall master project schedule and comment and advise the AOC/OCCM and court on the master schedules contents and time frames.

- Review and comment on the cost estimates developed at the end of the Working Drawings Phase and prepared by both the A/E and CM@R firms and participate in cost control management of the project to insure that the project can be constructed for the authorized budgeted amount.

- Participate in and contribute to value engineering and value analysis exercises as required.

- Coordinate and contribute to constructability and peer reviews of the project.

- Prepare Department of Finance (DOF) and State Public Works Board (SPWB) documents and monitor and facilitate their approvals.

- Monitor and facilitate project approvals with the Division of State Architect (DSA), State Fire Marshall, and Corrections Standards Authority (CSA).

- Review and provide input on the solicitation for sub-contractor bids.

- Monitor subcontractor bid advertising and participate in any outreach to encourage participation of local subcontractors and vendors in the subcontractor prequalification process.

- Participate in the review of sub-contractor proposals.

- Provide analysis of bids compared with the project budget and estimate(s).

  - Construction Phase:

- Revise and update the overall master project schedule and comment and advise the AOC/OCCM and Court on the master schedules contents and time frames.

- Review general contractor’s construction schedule and make recommendations as to its accuracy.

- Attend and participate in the pre-construction conference.

- Attend all on-site construction meetings.

- Review and comment on all meeting minutes recorded by the Contractor.

- Observe construction and make recommendations to the AOC/OCCM Design and Construction Regional Manager concerning construction progress, quality of construction, and conformance with the contract documents.

- Review, evaluate, recommend, and report to the Project Director, AOC/OCCM Design and Construction Regional Manager, and court all Requests for Information (RFI) prepared by the Contractor that may substantially impact the operational character of the court, project schedule, or project budget or that are not in conformance with AOC/OCCM court design and construction standards.

- Review, evaluate, recommend, and report to the Project Director, AOC/OCCM Design and Construction Regional Manager, and court all Change Order Requests (COR) prepared by the Contractor that may substantially impact the operational character of the court, project schedule, or project budget or that are not in conformance with AOC/OCCM court design and construction standards.

- Review, evaluate, recommend, and report to the Project Director, AOC/OCCM Design and Construction Regional Manager, and court all Change Orders (CO) prepared by the Contractor that may substantially impact the operational character of the court, project schedule, or project budget or that are not in conformance with AOC/OCCM court design and construction standards.

- Archive and maintain all RFI, COR, and CO records.

- Manage and facilitate all submittal approvals.

- Manage and facilitate collection and review of certified payrolls, related labor compliance documents and any labor compliance related Public Record Act (PRA) requests.

- Thoroughly review and evaluate all payment applications submitted and comment and record concerns.

- When payment application is acceptable, sign approval recommendation for AOC/OCCM Project Director to formally approve and sign.

- Participate in claims analysis and negotiation if necessary.

- Participate in the commissioning and acceptance testing process insuring that building systems function as required.

- Insure that full building documentation per the general contractor’s contract and operational materials are received from the general contractor and are available for turnover to the AOC/OCCM’s Facilities Management Unit.

  - In Addition the Service Provider Shall:

- Provide all necessary expertise and services to professionally and diligently prosecute 	the work authorized.

- Contract for or employ at Service Provider's expense, subcontractors to the extent 	deemed necessary for the work.

- Consult, for all phases of work as necessary, with normal and customary employees, 	agencies, and/or representatives of the State regarding the work of each Work Order.  	These include but not limited to AOC’s division and unit partners such as the 	Facilities Management Unit, Office of Emergency Response Services, Information 	Technology Unit, and Audio Visual Unit.

- Update the Project Management Plan as required as project progresses through each 	project phase.

- Prepare and issue Monthly Project Progress Reports summarizing progress and 	identifying issues of concern using the format and content requirements provided by 	AOC/OCCM.

- Attend meetings with the State, court, other professionals employed by the State and 	local and regional agencies as needed and directed to perform the work.

- Prepare and issue meeting minutes documenting decisions and required action items 	for project meetings attended.

- Work effectively with other State agencies, including but not limited to Division of 	the State Architect, State Fire Marshall, and Corrections Standards Authority in 	approving the project for construction and during construction.

- Cooperate and collaborate with other professionals employed by the State for 	related work including but not limited to the A/E firm and CM@R firm 	selected for  	the project.

- Review site surveys, available site-related literature, and previously prepared project 	reports furnished to Service Provider or obtained by Service Provider pursuant to this 	Agreement and advise OCCM by written report or memo whether such data are 	sufficient for purposes of design and/or construction, or whether additional data are 	necessary.

- Abide by all regulations imposed by funding sources, such as auditing requirements 	and payroll affidavits.

- Provide a professional level of review of all deliverables to assure quality, technical    	accuracy, and the coordination of all work and documents furnished by Service 	Provider under this Agreement.  Service Provider shall, without additional 	compensation, correct or revise any errors in its work or documents.

END OF EXHIBIT

Exhibit E

SERVICES REQUEST FORM

This Services Request is made by the Judicial Council of California Administrative Office of the Courts (“AOC”) under Agreement @ with @Contractor N&A.

State to Complete:

The State’s Project Manager for this Services Request is:

Name: ____________________________

Address:___________________________

Phone: ____________________________

Fax:   _____________________________

OCCM Request No. ______

Date of Submission of OCCM Request: __/__/__

Contractor Required Proposal Date (5 Business Days following date of receipt): __/__/__

Work Order Details:

Description of Work Requested: ______________________________________________________________________________________________

______________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

Is the Work to be provided on a Deliverables Basis?

- Yes      No

- Requested Dates of Performance:

- Start of the Work:__/__/__

- Completion of the Work:  __/__/__

- How is the Work Order to be Paid for?

- Fixed Price Basis

- Time and Materials Not to Exceed Basis

- Contractor to Complete:

The Contractor’s Project Manager for this Work Order shall be:

Name: ____________________________

Address:___________________________

Phone: ____________________________

Fax:   _____________________________

Agreed to Description of the Work (Statement of Work): ___________________________________________________________________________________________

_______________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- Agreed to Modified Dates of Performance:

- Start of the Work:__/__/__

- Completion of the Work:  __/__/__

- Detailed Project Schedule Attached

| Date Scheduled | Responsible Party | Activity |
| --- | --- | --- |

- Key Personnel to be Assigned to the Work:

- (Identify Subcontractor personnel)

- __(Name, Title)_____________________

- _________________________________

- _________________________________

Price: ____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

- If payment is based on Deliverables, Provide a Payment Schedule:

| - Payment Amount: | - Description of Deliverable: |
| --- | --- |
| - $ |  |

- Grand Total:  $________

- Designated Subcontractor(s):

- Name and Address___________

- Name and Address___________

Date of Contractor’s Proposal: __/__/__

END OF EXHIBIT

State of California					WORK ORDER

| Work Order Number @Business Svcs to supply | Amendment Number |
| --- | --- |
| TAXPAYER’S FEDERAL EMPLOYER IDENTIFICATION NUMBER |  |

STANDARD AGREEMENT —

STD. 2 (REV.5-91)  ID/IQ CM (7-6-06)

THIS AGREEMENT, made and entered into as of @ day h day of @month and year ("Effective Date"), in the State of California, by and between State of California, through its duly elected or appointed, qualified and acting

| TITLE OF OFFICER ACTING FOR STATE Business Services Manager |  |  |  | ENTITY Judicial Council of California, Administrative Office of the Courts 455 Golden Gate Ave. San Francisco, CA 94102 |  |  |  |  |  |  |  |  |  |  | , hereafter called the AOC”, and |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CONTRACTOR'S NAME |  |  |  |  |  |  |  |  |  |  |  |  |  |  | , hereafter called the Contractor. |
| WITNESSETH: That the Contractor for and in consideration of the covenants, conditions, agreements, and stipulations of the AOC hereinafter expressed, does agree to furnish to the AOC services and materials as follows: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Contractor is hereby authorized to, and shall provide the Work specified in the attached Work Order, OCCM Request # in accordance with the Agreement # and the Work Order. The amount the State may pay the Contractor under this Work Order shall not exceed $(Grand Total from WO).This period of performance of the Work specified in this Work Order shall commence @date and expire @date. [Optional}All Work that is provided by Contractor must be completed, and all invoices applicable to the Work must be submitted to and received by the AOC’s Accounts Payable department no later than May 15, 20 . The State will not be responsible for payment for Work performed or for invoices received following May 15, . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IN WITNESS WHEREOF, this Agreement has been entered into by the parties hereto, effective upon the Effective Date. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STATE OF CALIFORNIA |  |  |  |  |  |  |  |  |  | CONTRACTOR |  |  |  |  |  |
| ENTITY Judicial Council of California, Administrative Office of the Courts |  |  |  |  |  |  |  |  |  | CONTRACTOR (if other than an individual, state whether a corporation, partnership, etc.) |  |  |  |  |  |
| BY (AUTHORIZED SIGNATURE)  |  |  |  |  |  |  |  |  |  | BY (AUTHORIZED SIGNATURE)  |  |  |  |  |  |
| PRINTED NAME OF PERSON SIGNING Grant Walker |  |  |  |  |  |  |  |  |  | PRINTED NAME AND TITLE OF PERSON SIGNING |  |  |  |  |  |
| TITLE Senior Manager |  |  |  |  |  |  |  |  |  | ADDRESS |  |  |  |  |  |
| AMOUNT ENCUMBERED BY THIS DOCUMENT $@Buss Svcs to fill in |  | PROGRAM/CATEGORY (CODE AND TITLE) |  |  |  |  |  |  |  | FUND TITLE |  |  |  |  |  |
| PRIOR AMOUNT ENCUMBERED FOR THIS CONTRACT $0.00 |  | (OPTIONAL USE) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL AMOUNT ENCUMBERED TO DATE |  | ITEM |  |  | CHAPTER |  |  | STATUTE |  |  |  | FISCAL YEAR |  | EXEMPT FROM DEPARTMENT OF GENERAL SERVICES APPROVAL. |  |
|  |  | OBJECT OF EXPENDITURE (CODE AND TITLE) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| I hereby certify upon my own personal knowledge that budgeted funds are available for the period of the expenditure stated above. |  |  |  |  |  | T.B.A. NO. |  |  |  |  | B.R. NO. |  |  |  |  |
| SIGNATURE OF ACCOUNTING OFFICER  |  |  |  |  |  |  |  |  | DATE |  |  |  |  |  |  |
| CONTRACTOR | STATE ENTITY |  | DEPT. OF GEN. SER. |  |  |  | CONTROLLER |  |  |  |  |  |  |  |  |

exhibit G

ACCEptance and Signoff Form

For Work Order No. ____________

## Date submitted by Contractor:_____________

Deliverable Name: _________________

1) Submitted on time: [   ] yes     [   ] no.  If no, please note length of delay and reasons.

___________________________________________________________________________________________________________________________________________________________________________________________________________________________

2) Complete: [   ] yes     [   ] no.  If no, please identify incomplete aspects of the Work.

___________________________________________________________________________________________________________________________________________________________________________________________________________________________

3) Technically accurate: [   ] yes     [   ] no.  If no, please note corrections required.

___________________________________________________________________________________________________________________________________________________________________________________________________________________________

Please note level of satisfaction:

[   ] Poor     [   ] Fair     [   ] Good      [   ] Very Good      [   ] Excellent

Comments, if any:

__________________________________________________________________________________________________________________________________________________

[   ] Work is accepted.

[   ] Work is unacceptable as noted above.

Name:________________________________________

#### Title:_________________________________________

#### Date:____________

END OF EXHIBIT

END OF AGREEMENT